CAUSES OF DELAY AND COST OVERRUNS IN PUBLIC SECTOR BUILDING CONSTRUCTION PROJECTS IN PUNJAB

By

Mansoor Akbar (MSPM-III)

Roll. No:03-298142-015

Department of Management Sciences

A thesis presented to Bahria University, Islamabad in partial fulfillment of the requirements for the degree of Master of Science in Project Management

March 2016

CERTIFICATE REGARDING INCORPORATION OF CORRECTIONS/ MODIFICATIONS IN MS DISSERTATION AS SUGGESTED BY THE REVIEWERS/ EXAMINERS

I, Mansoor Akbar, having enrollment No. 03-298142-015 student of MSPM, Department of Management Science, Bahria University Lahore Campus, hereby certify that I have incorporated all corrections, modifications and suggestions recommended by the external and internal reviewer/ examiner in my MS dissertation titled “CAUSE OF DELAY AND COST OVERRUNS IN PUBLIC SECTOR BUILDING PROJECTS IN PUNJAB”. These modifications in my MS dissertation/thesis have been made in consultation with my principal supervisor and he/she is satisfied that all the changes have been incorporated.

The FIVE number of copies of the final version of thesis are submitted herewith.

Undertaking by:					Certified and countersigned by

Principal Supervisor:

(MANSOOR AKBAR)			               (Dr. Ghulam Mohey-ud-din)

Roll No. 03-298142-015	                                          Designation: Acting Head of

MSPM Spring 2016			                             Management Sciences Department

Bahria University, Lahore.	                             Department: Bahria University,							               Lahore

(Dr. Ghulam Mohey-ud-din)

Acting Head of Management Sciences,

Bahria University, Lahore.

SUBMISSION FORM OF THESIS FOR HIGHER RESEARCH DEGREE BAHRIA UNIVERSITTY, LAHORE

Candidate Name: Mansoor Akbar (MSPM-III)

I submit 4 Copies of thesis for examination for the degree of MS, Thesis Titled:

Causes of Delay and Cost Overruns In Public Sector Building Construction Projects in Punjab

Candidate Signature: _______________________ Date: _______________________

Certificate of Principal Supervisor

I Dr Ghulam Mohiyuddin being the principal Supervisor for the above student certify that thesis is in a form suitable for examination and that the candidate has pursued his course in accordance with the Rules of the University.

Signature: _________________________________ Date: ______________________

Recommendation for Examination

I recommend that the thesis be examined.

Principal Supervisor: __________ ______________ Date: _____________________

Co-Supervisor:_____________________________ Date: _____________________

Not Recommended for Examination

I recommend that the thesis be examined.

Principal Supervisor: ________________________ Date: ___________________

Co-Supervisor:_____________________________ Date: __________________

Statement by the Head Faculty/Department

I support the submission of the thesis of the above named student for examination under the University Rules for higher degrees.

Signature: ________________________________ Date: _________________

APPROVAL SHEET

SUBMISSION OF HIGHER RESEARCH DEGREE THESIS

Candidate‘s Name: 		Mansoor Akbar

Discipline: 			Project Management

Faculty/Department: 	Department of Management Sciences

I hereby certify that the above candidate’s work, including the thesis, has been completed to my satisfaction and that the thesis is in a format and of an editorial standard recognized by the faculty/department as appropriate for examination.

Signature(s):

Principal Supervisor: Dr. Ghulam Mohiyuddin

Date: 29th February 2016

The undersigned certify that:

- The candidate presented at a pre-completion seminar, an overview and synthesis of major findings of the thesis, and that the research is of a standard and extent appropriate for submission as a thesis.                                                                                                              2.   I have checked the candidate‘s thesis and its scope, format; editorial standards are recognized by the faculty/department as appropriate.                                                                        Signature(s): Dean/Head of Faculty/Department:                                                               Date: _____________________

DECLARATION OF AUTHENTICATION

I, Mansoor Akbar, Student in the Department of Management Sciences, Bahria University. Islamabad, certify that the research work presented in this thesis is to the best of my knowledge as my own. All sources used and any help received in the preparation of this dissertation have been acknowledged. I hereby declare that I have not submitted this material, either in whole or in part, for any other degree at this or other institution.

Signature: _____________________

Name: Mansoor Akbar

DEDICATION

This thesis is dedicated to all of my family members.

MY FATHER

For earning an honest living for us and for supporting & for encouraging me to believe in myself

MY MOTHER

A strong & gentle soul who taught me to trust in Allah, believe in hard work and that so much could be done with little but true efforts

MY ELDER SISTER

For being my first teacher and for providing me with the strong love shield that always surrounds me and never lets me down

MY WIFE

For being my companion & my support during my education career, She has been a constant source of confidence and inspiration for me.

RESPECTED INSPECTOR GENERAL OF PRISONS

Mr. Mian Faruq Nazir has been my support during my degree of MSPM, without his constant source of moral support and inspiration for me, I couldn’t complete my degree.

ACKNOWLEDGEMENT

There are a number of people without whom this thesis might not have been written, and to whom I am greatly indebted. Foremost, I would like to express my sincere gratitude to my advisor Dr. Ghulam Mohiyuddin and Head of Department Dr Rizwana Bashir for the continuous support of my Master‘s study and research, for their patience, motivation, enthusiasm and immense knowledge. Their guidance helped me in all the time of research and writing of this thesis. I could not have imagined having a better advisor and mentor for my Master study.

Besides my advisor, I would like to thank Mr. Nauman and Mr. Rabnawaz Lodhi for their encouragement, insightful comments and hard questions. Loving thanks to my parents, who played such important roles along the journey, as they engaged in making sense of the various challenges we faced and in providing encouragement to me at those times when it seemed impossible to continue. I offer my gratitude and appreciation to them.

To my friends Mr. Masood Akhter (P & D) and Mr Mian Nadeem (my session fellow in UET, Lahore) who have been a source of encouragement and inspiration to me throughout my research, a very special thanks to them for providing a ―writing space and for nurturing me through the months of writing and also for the myriad of ways in which, throughout my data collection, you people have actively supported me in my determination to find and realize my potential, and to make this contribution to my world.

Last I want to thanks my loved ones and my friends for supporting me throughout the period of my study.

ABSTRACT

Construction projects are the main component of Infrastructure developments. It is continuing practice in developing countries for the development and growth of the nation. But it is highlighted in the literature that there are almost more than 50% projects which have to face delays and overrun cost. In developing nations like Pakistan, it is very difficult to manage these issues which ultimately affect general public by imposing extra taxes and inflation. This study has main objective to identify the main causes of overrun cost and delay in public projects and also compute the severity index for these factors. In this study there are main three factors of delaying in projects; poor planning, insufficient site supervision and lack of harmonization in different departments. A sample of 110 different stakeholders (clients, project directors, monitoring and evaluation team members etc.) were selected as respondents.  Response rate of this survey was 88.7 with overall reliability (0.959) of the tool and data. A well structured questionnaire was used in this study having three main sections on the three potential factors of delay. Findings of this study have shown that there is strong correlation between these three factors of delay and overrun cost.  On the other side severity index of 52 sub factors or sub components have shown that poor planning, poor scope of projects, poor supervision and management at site and frequent changes of scope in the projects due to clients are the main causes of delay and most occurred reason in the projects.  Overall factors analysis shows that poor planning is most severe and frequently occurred factor of delay in public sector projects. Poor site supervision and lack of interdepartmental communication got second and third position in severity index. Overall this study concludes that stakeholders have to work on the planning and execution of projects to overcome the overrun cost and delay in construction projects.

TABLE OF CONTENTS

1. Introduction ..................................................................................................................... 11

1.1 Research Problem statement.............................................................................. 12

1.2 Research Objectives .......................................................................................... 14

1.3 Research Hypothesis .......................................................................................... 14

1.4 significance of study…………………………………………………………….16

2. Literature Review .............................................................................................................17

3. Research Methodology .....................................................................................................27

3.1 Type of investigation ………………………...…………………………………27

3.2 Research Design ............................................................................................... .27

3.3 Targeted Population ......................................................................................... .28

3. 4 Sampled population……………………………………………………..…….28

3.5 sampling ………………………………………………………….……..……..28

3.6 sample size estimation ………………………………………………………....29

3.7 Response rate……………………………………………………………..……30

3.8 Data collection method .................................................................................... 30

3.9 Pre testing……………….……………………………………………..………30

3.10 Data Collection procedure … ........................................................................31

3.11 Data analysis Techniques……..…………………………………..…………31

4. Data collection and analysis.......................................................................................... 33

4.1 Reliability Analysis …………………………………..…………..…………..33

4.2 Response rate of the survey……..................................................................... 34

4.3 Role of Respondents in the organization ………………………….………….35

4.4 Poor Planning ……………………………...……………………...…………..36

4.5 insufficient site supervision……………………………………..…………….38

4.6 Lack of interdepartmental communication ……………………..…………….42

4.7 Correlation analysis ……………………………..…………………………….44

4.8 Severity Index……………………...…………………………..………………47

5. Findings ......................................................................................................................... 52

6. Conclusion ..................................................................................................................... 55

6.1 Recommendations/Suggestions ...................................................................... 56

6.2 Limitations of Study…………………………..………..…………………….57

References ....................................................................................................................... .58

Appendix ......................................................................................................................... .63

LIST OF FIGURES

Figure1.1 Theoretical model of study ……………………………………………………….15

Figure 4.1 Pie chart for Designation or Role of respondent in the organization …………….35

Figure4.2 Correlation matrix …………………………………………………..………….....46

Figure 4.3 severity index bar chart for Poor planning sub components ……………………..48

Figure 4.4 severity index bar chart for insufficient supervision at site sub Components …………………………………………………………………..............................................49

Figure 4.5 severity index bar chart for Lack of interdepartmental communication sub components…………………………………………………………………….......................50

Figure 4.6 Severity index bar chart for all main components or factors…...................……...51

LIST OF TABLES

Table 4.1 SPSS Statistical Reliability Analysis…………………………………………..….33

Table 4.2 Response rate of survey…………………………………………………………...34

Table 4.3 Frequency distribution of Poor planning sub components……………………….36

Table 4.4 Frequency distribution of insufficient supervision at site sub components… .…..39

Table 4.5 Frequency distribution of Lack of interdepartmental communication sub components

………………………………………………………………………………………………..42

Table 4.6 Normality test for main three factors of study.…………………………………...45

Table 4.7 Spearman Correlation analysis table.…………………………………………….47

- Introduction:

Infra structural development is the main component of groomed economy. It always needs lot of attention and supervision from different departments for proper execution. In developing countries infrastructural development like roads, buildings, bridges etc. are on the way. But it is quite unfortunate that majority of building construction projects in public sector fail to meet the cost and schedule baselines. This phenomenon is equally applicable to all levels of projects i.e.; from major, capital to mega projects. Due to this unhealthy and contaminated trend, the construction industry has virtually become infamous across the globe. Delays and Cost overruns are common in every project especially in public sector of countries.

Pakistan is also a country which belongs to the list of developing countries. Overrun of cost and delay in the projects can also be seen here.  Numerous studies have been conducted throughout the world about the causes and consequences of delay in the world. Various factors are associated with the construction and functioning of mega projects in Pakistan. According to the World Bank (1990), even for 1627 projects completed worldwide between 1974 and 1988, the overrun varied between 50% and 80%. Construction industry in Pakistan is still under exploited as it is based on traditional project delivery systems.

The  problems  faced by the  construction  industries  of  developing countries as lack of supervision  including: shortage of materials, unskilled personnel, non availability of adequate equipment , inadequate technology development, poor institutional development; predominance of small and weak local firms, unsatisfactory procedures and contract documentation, and highly unstable levels of demand and output. Delays can lead to many

11

detrimental effects such as lawsuits between owners and contractors, increased costs, loss of productivity and revenue, and contract termination.

Construction sector, the world over, is considered to be a basic industry on which the development of the country depends. To a great extent, the growth of a country and its development status is generally determined by the capacity of its construction companies to successfully complete mega building projects. Pakistan is a developing country that is currently enjoying relatively strong growth in construction activities. Construction, today, is the second largest sector in Pakistan’s economy after agriculture. According to the report of the Economic Survey of Pakistan, 2006-2007, the real GDP growth for the last economic year has been powered by stellar growth in construction by 17.2 percent.

  - Research Problem Statement

Pakistan is a developing nation. Usually Pakistan imports majority of technology and latest tools in every field; medicine, agriculture, civil engineering, computing, IT etc. as Pakistani nation, we are lacking in application of technology in every field. The methods and techniques used in majority of construction are conventional which are not time efficient. During the construction of any project there are a number of variables involved. Some of the variables that significantly influence the efficiency of construction are inappropriate planning, lack of supervision and inadequate interdepartmental communications, environmental factors, financial problems, political influence, inflation etc. Problems faced during execution are that no two projects are similar so the management faces a lot of uncertainties. These uncertainties and factors may result in delays and cost overruns which can be reduced but cannot be eliminated completely.

12

Pakistan has to face many problems since it came into existence. One of the main problems is the political system which is very unstable. Changes of regime have taken place many times in the past. The importance and viability of projects initiated under one government are not properly communicated to next regime. It has been observed that the new government stops the funding of the existing or continuing projects, which the past government had initiated. Moreover, centralized system of approvals is another reason of

delay subsequently resulting in cost overruns. A stable government system with effective management is necessary for the regular funding of construction projects. Pakistan has been unfortunate in this area.

Almost all the public sector projects face delays and cost overruns. Its roots are deep and these are spreading wider with passage of time. Generally, the impact of the problem is significant in developing countries where the parties of the project are financially weak. These delays and cost overruns adversely affect the construction industry and in return functioning of new organization, would be using the particular building.

Another aspect in the developing nations is that, overrun cost and delay creates multidimensional effects on the economy of countries. This overrun cost is managed through different ways especially in Pakistani context by increasing taxes and other collection from the public. It will ultimately create a situation of inflation and different social, psychological and other related problems in the masses. Keeping in all these things in mind this study was planned to highlight such factors which have severe effects on overrun cost and delay.

13

1.2 Research Objectives

To identify main causes of delays and cost overruns of building construction projects in Punjab and then rank them according to their severity of these delaying factors on functioning of new public sector projects.

Main objectives are

- To study and evaluate the causes of delay which lead towards cost overruns in construction projects of Pakistan.

- To see the relationship between different factors of delay

3. To classify and rank the identified causes corresponding to their effects in different construction projects of new Public sector projects.

1.3 Research Hypothesis

Poor planning, improper supervision and lack of interdepartmental communications cause delays and cost overruns in public sector construction projects in Punjab.

H1:  Poor planning is a significant cause of project delays & cost overruns.

H2:  Lack of interdepartmental communications is a significant cause of delays & cost overruns.

H3:  Ineffective supervision is a significant cause of project delays & cost overruns.

Independent Variables: Poor planning, Lack of interdepartmental communications, Ineffective supervision.

14

Theoretical Model of study:

Figure 1.1 Theoretical model of study for delays and cost overrun in public projects

Source: (Made by Researcher)

15

1.4 Significance of study

Pakistan is in the transition phase of development due to its political, democratic, financial crisis from last few decades. So this country is not in the position for comprising against overrun cost and unplanned delays in public projects which subsequently affects the whole economy of country.  Current study will highlight the reasons which cause delays and cost overruns in construction projects in public sector. The recommendations in this study after tested results will persuade clients to ensure timely supply of funds, and to have adequate financial controls to avoid delays and cost overruns. In light of results at the end of study, consultants and clients may take prompt decisions for timely approvals. Contractors may improve contract management skills.  The government shall evolve stringent mechanisms and policies to arrest unhealthy trends in construction management leading to delay and projects’ failures. In Pakistani context this academic activity will be addition to the knowledge for those who continue research in this stream.

16

- Literature Review

Review of literature is the process of extraction of suitable information from previous researches for your own research. The purpose of this chapter is to identify past studies and review which determine the factors responsible for cost overruns and delays of construction projects. It also highlights the percentage of delaying projects in different economies of the world.

The construction industry occupies paramount importance in most economies. But construction projects are notorious for delay and cost overruns. Numerous works have been done to root out the cause of delays in completion. Various statistical methods were used to find the most important causes. The factors responsible for delay are different for different countries, and even for different types of projects within same region or area. The causes of delay are selected from literature. The construction industry is also recognized for providing and creating huge number of jobs and considerable opportunities for economic development of a country. (Haseeb, Lu, Hoosen, & Rabbani, 2011) considers the deviations of projects from their baselines as the biggest danger to construction sector. Government is the main and prime customer in the industry of construction in all countries (Okpala & Aniekwu, 1988). Literature has shown that majority of government projects are delayed and this delay usually results in completion of projects beyond intended time and estimated cost. This situation is not favorable for the contractors, consultants, owners and other stakeholders (Odeh & Battaineh, 2002). The dilemma of Public sector projects is that contracts are awarded to the lowest bidder. This practice is usually not being implemented in developed countries. According to report written by Latham (Latham, 1994) clients always want to ensure that projects are delivered to them in given frame of time. Projects completed after their planned dates had to face ruthless criticism (Flanagan, Norman, Ireland, & Ormerod, 1986). On the

17

other side timely completion of construction projects is the gauge of their efficiency and effectiveness.

To understand the concept of delay and overrun cost, first researcher has to understand the phases of projects. Usually there are three phases of construction projects consisting of project conception, project design and its construction. The third phase viz construction is the major causative factor for time overruns during which unexpected situations arise (Chan & Kumaraswamy, 1997). Usually the delay is considered as time beyond which project is completed against the agreed upon cutoff date specified in the agreement among the stakeholders. The vendor experiences revenue loss due to this delay. There are multiple types of losses in practical scenario; like in some instances contractor has to sustain loss due to inflation, increase in labor and material costs in each financial year and between these durations.

There are many random variables responsible for project delays. These unpredictable factors may be stakeholders’ performance, non-availability of funds and non-conducive environmental conditions (Assaf & Al-Hejji, 2006). This shortage of funding may also cause cost and time overruns resulting in disappointment of Clients (Kaliba, Muya, & Mumba, 2009). As cited by (Ahmed, Azhar, Castillo, & Kappagantula, 2002), time overruns in construction projects are a worldwide experience which are followed by cost overstrains. All this leads to adverse relations among contractors and contractors causing mistrust, legal actions, mediation from third parties and an impression of fear. It also creates trepidation towards other stakeholders (Ahmed et al., 2002). Acceleration and expansion of delayed projects is not wholly experienced in developing countries but it also exists in developed countries. A sum of a percentage of project cost is reserved as emergency reserve by mutual

18

approval of the parties (Akinsola, 1996). But interpretation of clauses from different angles and dimensions elevate objections including question about demand of over payment by contractor due to delay by him  (Alkass, Mazerolle, & Harris, 1996). Project Manager usually takes the responsibility to complete the project within defined period and budget.

Literature has many studies which directly and indirectly reported many type of Issues related to delays and budget increase affecting project quality and efficacy. Capability to predict probable problems arising in present and upcoming projects is extreme requirement for project accomplishments and success (Long, Ogunlana, Quang, & Lam, 2004). If parties have consented upon the delivery of the project and construction work is completed beyond the date agreed upon date in planning phase, it results in expensive situation (O'Brien, 1976). A research has reported that Project time-line and efficiency are directly linked  with poor site supervision and time management (Pickavance, 2000).

First researcher has a look on the overrun cost and percentage of delayed projects in different regions of the world so that this problem nature and volume can be estimated. According to a research the percentage of delayed construction projects in KSA and UK was more than 70% and 60% respectively  (Emam, Farrell, & Abdelaal). In order to investigate the problem of cost performance worldwide for construction projects, (Flyvbjerg, Skamris Holm, & Buhl, 2003). They have studied 258 multi nation projects (20 nations) with an estimated worth of US$ 90 billion (size of projects range from US$ 1.5 million to 8.5 billion) and concluded that cost intensification was a common practice and happens in almost nine out of 10 projects with an average of 28% higher than planned and forecast costs. They also concluded that average cost rise in Europe was 25.7%, North America 23.6% and other geographical areas was 64.6%, while cost performance in construction projects has not

19

improved over time.  Similar sort of situation had been observed 70 years ago. World Bank also stated that 63% of the 1778 construction projects in different countries faced poor performance with overrun in budget at an average of 40% (Ameh, Soyingbe, & Odusami, 2010) and (Car-Pušić, 2010).

Another survey was conducted in United Kingdom by  (Olawale & Sun, 2010) and reported that many construction projects had to face cost overruns. Only 41% of respondents had participated in this survey and suffered cost overrun less than 10% of their cost projects. In other words it could conclude that remaining 59% of respondents experienced cost overrun more than 10%.

Similarly in Bosnia and Herzegovina, a study of 177 projects of structures highlighted that the 41.23% of structures’ agreed price was not achieved or met. Similarly another detailed investigation of 29 building construction structures depicted that deal price overruns were noted at 17 (58.62%) with maximum contracted price overrun of 29.16% with  average of 6.84% (Car-Pušić, 2010). A study in an African country Ghana has reported that 75% of the overall projects surpassed the original project cost and only 25% were completed within the given time frame and budget (Frimpong, Oluwoye, & Crawford, 2003).

Malaysia is famous for its infrastructural growth but the problem of cost overrun and time delay is a serious issue (Abdullah, Abdul Rahman, Azis, & Asmi, 2009). They mentioned that since 1984, 90% of large MARA construction project had to face delay with significant amount of time and cost overrun.

20

Now there are dozens of studies which have considered the causes of this overrun and delay in practical scenario. Cost overrun and delay in construction projects can occur due to various reasons as (Charoenngam & Sriprasert, 2001) explored that cost overrun was caused by inefficient and ineffective construction management and poorly launched cost control systems. Important consideration has been paid to a great pact for successful projects accomplishment in last two decades (De Wit, 1988).

A survey based research was conducted using questionnaire and distributed among clients, consultants, contractors and practitioners from relevant organizations. Significant factors were agencies delay in responses, alterations in designs during construction, ineffective control, lack of planning in pace and scope changes during construction. It is also concluded that construction projects delays and cost overruns is not a good practice in practical situations  (Emam et al. 2015).

Another survey of Turkish public sector departments and contractors working on these projects was carried out in 1970s and 1980s (Doloi, Sawhney, Iyer, & Rentala, 2012) Factors were identified by (Faridi & El‐Sayegh, 2006), which could be controlled by all stakeholders involved in public sector projects. Poor planning, delay in decision making and drawings caused delays in 50% projects in UAE, however such factors responsible for delay were not found in KSA and Lebanon where delay in approvals, slow decision making along with shortages of materials were the common reasons.

According to  (Al-Khalil & Al-Ghafly, 1999) lack of agreement between stakeholders was cause of delay in Saudi Arabia. This was also studied by (Al‐Kharashi & Skitmore, 2009) in Saudi Arabia. According to another study (Olawale & Sun, 2010), real causes and

21

measures were highlighted regarding causes of delay and cost overruns in UK. (Nkado, 1995) raised the issue of time performance of UK projects from contractors point of view. (Ling & Hoi, 2006) studied the working performance of contractors from Singapore and India for their cost and time performance. According to (Abd El-Razek, Bassioni, & Mobarak, 2008) main cause of delay in projects in Egypt was that stakeholders blamed each other for delay. He analyzed this by using importance index and spearman rank correlation, the same analysis was done by  (Assaf, Al-Khalil, & Al-Hazmi, 1995) who gave credit to the team effort for success in building projects. Thirty causes of delay under 7 main factors were identified by  (Lo, Fung, & Tung, 2006) in Hong Kong which included client, project engineer, contractor, human behavior, external factors, resource and project itself. He used rank agreement factor (RAF), percentage agreement (PA) and percentage disagreement (PD) in respect of various stakeholders on causes of delay.

Cohen, 2006; Zeybek & Kaynak, 2008 studied that mega projects are important in for sustainable development especially in most populous countries. According to different researches conducted (Ayman Othman & El-Gendawy, 2012; Field & Ofori, 1988; Mthalane, Othman, & Pearl, 2008) that infrastructure development of industry, transport, education, and health accomplishes the necessities of the individuals. According to  (Shore & Cross, 2005), multinationals from different architectural and historical background tailor these infrastructures according to the local environment of the state. Skill, capability, expertise and adequate funding for larger projects are missing in developing countries resulting in delays and cost overruns as pointed out by (Flyvbjerg, Bruzelius, & Rothengatter, 2003; Sturup, 2009), posing a huge challenge for project success.

22

According to (Haseeb, Bibi, & Rabbani, 2011), inadequate funds, impedimental decision making and lacking of close supervision in planning are reasons of planned overruns. Moreover (Han et al., 2009) Suggests that Project progress is enhanced by suitable tools and techniques, modern methods due to which rework, scrap and mistakes in design can be evaded.

According to (Apolot, Alinaitwe, & Tindiwensi, 2011) five main factors behind time delays in projects are scope change, late payments to contractor, inflation, poor site supervision and lack of capital. Another research conducted by (Sambasivan & Soon, 2007) and concluded that  there are different approaches for conduction of projects, their plans, subsidiary plans and construction. They highlighted that communication gap between inter department would create differences and ultimately delayed projects and their outcomes. Subsequently   efforts of managers, contractors and engineers did not create productivity in this environment. The situation is intensified when there is least coordination between architects/ designers and contractors, and every individual tries to fix to his own decision and verdict even if he/ she has erroneous thinking (Nawaz, Ikram, & Qureshi, 1985).

Apart from these, (Frimpong et al., 2003) studied the impact and contribution of 26 factors that could cause cost overruns in construction of ground water projects in Ghana. They found that monthly payments method had to face lot of difficulties and most important cost overruns factor. It is indicated by contractors and consultants, while owners ranked poor contractor management as the most important factor. In spite of this difference in viewpoints among these three studied groups, high degree of agreement among them was seen regarding ranking of the factors. Overall ranking results indicate that the three groups felt that the major factors that can cause excessive cost overruns in developing countries are material

23

procurement, poor contractor management, poor technical performances, monthly payment difficulties, and inflation in material prices.

Another questionnaire based survey conducted for high rise construction projects in Indonesia  (Kaming, Olomolaiye, Holt, & Harris, 1997).  Researchers found that inflated material cost, inaccurate quantity take-off and labor cost escalated due to environment restriction were the most important causes of cost overruns.

A Korean researcher has studied cost overrun problem in Korean social overhead capital projects. He selected 161 completed projects and explored that causes of cost overruns were found as delays during construction, changes in scope, irrational estimation decision and adjustment of project costs and absence of practical use of the earned value management system  (Lee, 2008).

(Charoenngam & Sriprasert, 2001) investigated that cost overrun problems in construction industry of Thailand stated that compromised quality materials cause elevated construction cost than expected due to loss of materials during process of construction. This is a consequence from a deficiency in standards of materials and management systems. Lack of ability of management to prevent cost overruns or to control construction costs caused many Thai construction companies to fail in achieving efficient cost performance in projects.

Another study of Malaysia, using questionnaire collecting data in different projects at Kelang Valley found that main factors that add to cost overruns include imprecise estimation of cost, underestimation of construction cost, poor project management, improper planning, lack of experience, poor contract management, inflation of project costs, high cost of

24

machineries, fluctuation in price of raw materials, unforeseen site conditions, insufficient fund, obsolete/unsuitable construction equipments and methods and mistake in design (Ali & Kamaruzzaman, 2010).

A study in Hong Kong indicated that the five principal causes of delays in projects are: poor site management and supervision, unforeseen ground conditions, delay in decision making involving all project teams, client-initiated variations and necessary variations of works (Chan & Kumaraswamy, 1997).

In a survey of the West Bank in Palestine, highlighted that the most severe factors affecting time delay in road construction projects from the owners’ perspective are: poor communication between construction parties, poor resource management, delays in instigation, insufficient inspection, and rework (Mahamid, 2011).

Examining the factors that cause delay in construction projects in Malaysia tested 31 variables. The main finding of the study was that financial factors are the most common cause of delays in construction projects in Malaysia. Lack of harmonization is considered the second most important factor causing delays, followed by materials problems (Alaghbari, Razali A. Kadir, Salim, & Ernawati, 2007).

(Al-Momani, 2000) investigated causes of delay in 130 public building projects constructed in Jordan during the period of 1990-1997. He wrapped up that the main causes of delay are related to designer or user changes, weather, site conditions, late deliveries, economic conditions and increases in quantities.

25

A study of Malaysia, (Sambasivan & Soon, 2007) investigated that ten most important causes of delays in the construction industry were: contractor’s improper planning, contractor’s poor site management, inadequate contractor experience, inadequate client’s finance and payments for completed work, problems with subcontractors, shortage in material, labor shortages, equipment availability and failure, lack of communication between parties, and mistakes during the construction stage.

(Mansfield, Ugwu, & Doran, 1994) studied the causes of delay and cost overrun in construction projects in Nigeria. The results showed that the most significant factors are financing and payment for completed works, poor contract management, changes in site conditions, shortage of materials, and improper planning.

Ample research  has been carried to find out causes of time overruns in several countries (Marzouk & El-Rasas, 2014). Suitability, relevance, budget adherence, quality and clients satisfaction are the indicators to measure project success and lack of these things are simply failure of projects. The cost management of a project comprises of careful estimation, making accurate budgets and control of costs by adherence to cost baseline (Guide, 2001). Project cost performance is estimated by variation between actual expenditure and funds authorized for the project (Yang & Chen, 2015).

26

- Research Methodology

Methodology is the path followed during any research. It is the set of activities carried out in a proper sequence. It elaborates the steps in chronological order. It is also defined as the process which is adopted for the conducting smooth research. There are different types of techniques and methods in the body of knowledge which are used in research. Usually there are three types of approaches which are followed in new era of research; qualitative, quantitative and mixed approach (Zikmund, Babin, Carr, & Griffin, 2012). Every methodology has its own important features. Like qualitative research is preferred in making theories and on the other side researchers prefer to follow quantitative methodology to get statistical and empirical evidence about the proposed hypothesis and objectives.  Mixed methodology is used when researcher wants to develop and test the theory regarding studied phenomenon. In this study quantitative methodology was used.

3.1 Type of investigation

This study is descriptive and explanatory in nature. It has addressed the main causes and factors of delay and cost overruns in public sector building construction projects. By covering this aspect it is descriptive research. On the other side it also focuses on the effect of different factors (independent variable) on cost and time (dependent variable) of projects. This part is considered as explanatory part of study.

3.2 Research design

There are different types of research design; cross sectional, before and after and longitudinal. Cross sectional design is used to see the current status of studies as it is also called status studies. On the other side when researcher wants to see the impact of some policy and intervention on some phenomenon then before and after study design is followed.

27

Similarly longitudinal study design is used when researcher wants to observe the trend and patterns of studied phenomenon (Zikmund et al., 2012). Current study is cross sectional as researcher has collected the information once and wants to just study the effect of different factors on cost and time of public construction projects.

3.3 Target Population

Population is defined as collection of individuals and organizations etc. target population is defined as it is larger group on which researcher wants to generalize the study results (Zikmund et al., 2012). Study title has shown that this study focuses on the Punjab level public projects. So all the public level projects constructed in Punjab are considered the target population of this study.

3.4 Sampled Population

Sampled population is usually subset of larger part (target population). Most of the time researchers have limited resources in research. Due to this situation larger part will not be covered in practical scenarios so a researcher has to concentrate on smaller part of the target population. Sampled population is defined as part of population from which sample is selected. In this study Lahore district was dealt as sampled population.  Lahore district is amongst the largest district of Punjab province and majority of public projects have been conducted in this district. So this district was considered as sample population of study.

3.5 Sampling

Sampling is process of selecting a sample from the population. There are two types of sampling; probability and non probability. Probability sampling is also called random sampling. In this type of sampling every unit of the population has equal or some chance of selection. On the other side biased approach is usually followed in the non probability

28

sampling (Kumar, 1999). Due to its biased approach this type of sampling is not preferred as its results cannot be generalized. In this research, researcher has used probability sampling. A complete list of approved projects has been obtained from Planning and development department Punjab and considered as sampling frame of the study. Simple random sampling was used in this study.

3.6 Sample size estimation

A complete list of approved projects from P & D department was obtained after sending the request as it was also a public information. It has approved approximately 3700 projects in the financial year of 2015-16. To get the representative sample from this list researcher used the formula given by (Yamane, 1967).

n= N/1+Ne2

Where    “n” is sample size

N= Population size

e= margin of error, 10% was margin of error in this study. In such studies where researcher has threat to get low response rate, margin of error can be increased (Zikmund, 2012).

Here according to this formula sample size was 98. But in pre testing it was observed that response rate was 76%. To mange this non response (24%) actual sample was inflated to 24% and it becomes 124. If actual study has low response rate then it would effect the reliability and validity of findings of study.

29

3.7 Response Rate

In this study 124 projects head, consultants, clients and responsible persons were identified by simple random sampling and questionnaire was sent through email and face to face methods. After that 110 questionnaires were returned and researcher got 88.70% response from field that was acceptable according to threshold % defined in theory of research.

3.8 Data collection tool

There are different methods of data collection; observation, interview, focus group discussions and questionnaire. Questionnaire is usually used when researcher wants to test the hypothesis and needs quantitative data. Questionnaire is main tool of quantitative approach of data collection.  In this study on the basis of previous literature researcher has developed data collection instrument for the study. This tool has two main parts; demographic information and second part has dealt with important factors of delay and overrun of cost in public sector projects. Five point likert scale has been used in the second part of instrument. These 5 points scale, where 1=Strongly Agree, 2=Agree, 3=Neutral,  4=Disagree, 5=Strongly Disagree.

3.9 Pre Testing

Pre testing is process of validation of questionnaire or data collection tool. It is usually used to check the validity of tool by following rules and principles; avoid sensitive, ambiguous, double barrel, double negative etc. questions defined in literature. After the completion of questionnaire,   5% of sample size, that was 6 respondents were face to face interviewed to review the basic guidelines of questionnaires. After this process few amendments like; changing of difficult words to easy words, two double barrel questions

30

converted into simple statements etc. had been identified and reported. Mandatory changes had been incorporated into this draft and finalized the questionnaire for final data collection.

3.10 Data collection Procedure

There are different approaches which are used in collection of data like face to face surveys, telephonic surveys, electronic surveys, mall surveys etc. Every method of data collection has advantages and disadvantages in practical scenario. In this study researcher has used face to face and electronic method for data collection.  Firstly in pre testing phase, electronic method was adopted and got low response rate from respondents. After that it was decided that face to face method would be beneficial in getting good response rate. But to manage the cost, electronic method was also used where it was applicable. Because we have used simple random sampling in selecting the respondents of study who were located in different geographical locations of Lahore district, so it was rationally very difficult to approach them physically. To overcome this issue electronic method was also adopted and used.

3.11 Data analysis Techniques

In this study Data analysis was divided into four sections; demographic analysis, descriptive part, correlation analysis and regression analysis.  Demographic variables were presented in the form of frequency distribution and percentages. On the other side mean, standard deviation, minimum and maximum values were calculated for quantitative variables in descriptive sections. Pearson correlation analysis was performed to see the relationship between main variables after checking the assumptions of normality. In the last section severity index was assessed and ranked the main three factors of overrun of cost and delay on public construction projects.

31

There are different methods to check the reliability of data; Cronbach’s Alpha is a one of them which is most popular. It is recommended that it should have value above than 0.7. On the other side for Frequency distribution is a descriptive technique which is used to present qualitative information in reasonable manner. Bar chart and pie chart is also used in this study for graphical presentation of qualitative data. Kolmogrove smirnove test is used for checking the assumption of normality before the application of correlation test. Correlation scatter matrix is also used to see the graphical view of correlation among variables. At last severity index was also used at the end of next chapter by using this formula. This is given here and also used by (Ayudhya, 2011)

Severity index = ¼ {w1x1+ w2x2+ w3x3+ w4x4 / w1+ w2+ w3+ w4} X 100%.

32

- Data collection and Analysis

This chapter is dealt with data analysis and results of the study. Firstly this chapter has reliability analysis of the questionnaire and collected data, after that response rate was discussed. Next section is about the demographic analysis and description of frequency tables for main three factors under study. Correlation analysis is also performed and described in the next part. Last part will deal with severity index and rank these three factors according to its importance and contribution in the delay of projects.

  - Reliability Analysis

| Sr. No | Construct | Number of items | Cronbach's Alpha |
| --- | --- | --- | --- |
| 1 | Poor planning | 12 | 0.838 |
| 2 | Insufficient site supervision | 26 | 0.921 |
| 3 | Lack of interdepartmental communication | 14 | 0.908 |
| 4 | Overall items | 52 | 0.959 |

Table 4.1 SPSS Statistical Reliability Analysis

Source: (Computed by Researcher)

33

Reliability of data is very important for the generalization of results which have been drawn on the basis of sample data. This table is regarding the reliability of collected data. It has three constructs which has different questions and representing a factor. Last row of the table is about overall reliability of the tool and data. First factor is poor planning which has 12 dimensions or items and its reliability coefficient is 0.838. This value is higher than threshold which is usually 0.70. Second construct in this study is insufficient site supervision which also has Cronbach’s alpha value 0.921 which is very good and shows that this construct has obtained reliable information. Lack of inter departmental communication has got reliability coefficient value is 0.908. Overall reliability of the tool and data is 0.959 which is higher than recommended value. It is concluded from this table that this collected data is reliable and its results can be generalized on the target population.

4.2 Response Rate of the survey

| Total respondents sampled | Sample actually Responded | Response Rate |
| --- | --- | --- |
| 124 | 110 | 110/124= 88.70% |

Table 4.2 Response rate of survey

Source (Calculated by Researcher)

This table has information about response rate of current survey. There were total 124 respondents in this study but 110 responded and gave the information regarding this survey. Response rate was 88.70% in this survey. This percentage is higher than threshold or recommended value.

34

4.3 Designation or Role of respondent

Figure 4.1 Pie chart for Designation or Role of respondent in the organization

Source (Made by Researcher)

This pie chart is the only single characteristic about the demographics of respondents. There are mainly five categories; consultant, client, PD or manager, M &E officer, contractor and others. Equal sample has been selected from each category (25 respondents). Lowest response was obtained from project director or manager and highest response from other category members of the sample. Sample of 110 was distributed among 6 categories.

35

4.4 Poor Planning

In this study first important factor of cost overrun and delay is the poor planning. This factor has been estimated by using questions or statement. These statements are dimensions of this concept. These statements were responded by respondents on 5 point likert scale. First

dimension about poorly defined scope of the project is the reason of cost overrun and delay in construction projects of Punjab.  Results have shown that approximately 96% respondents belonging to different categories agreed on this statement and remaining very minute 4% did not. Similarly inadequate planning has also similar sort of consensus on the given statement like poorly defined scope of project. First two dimensions got maximum agreement of respondents as they said that they were strongly agreed with these two factors of delay and cost overrun.  On the other side other problems were also considered as important for delays but less than these two which have been described earlier in this paragraph. A small percentage of Respondents said that geological conditions, environmental factors were not a factor for creating delay and overrun cost. Similarly few respondents also disagree with the statement that Discrepancies and / or deficiencies in contract documents may lead to cost overrun and delay. Other dimensions are also important as respondents also agree on these statements and factors. Overall it can be concluded that poor planning is very crucial and has significant role in causing delay and overrun cost.

| Sr. # | Questions | Strongly agree | Agree | Neutral | Disagree |  | Strongly disagree |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Poorly defined scope would cause time delay and cost overruns in the projects. | 58.2 | 37.3 | 2.7 |  | 1.8 | - |
| 2. | Inadequate planning will lead to delays and | 56.4 | 39.1 | 2.7 |  | 1.8 | - |

36

|  | Cost over runs in the project. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 3. | The confusing and ambiguous requirements by the client will cause delays and cost overruns in the project. | 32.7 | 56.4 | 6.4 | 4.5 | - |
| 4. | The improper feasibility study provided by the client would result in delay and cost overruns of the project. | 33.6 | 52.7 | 7.3 | 6.4 | - |

| 5. | Unclear project objectives by the client will lead to delay and cost overruns of the project. | 38.2 | 44.5 | 10.9 | 6.4 | - |
| --- | --- | --- | --- | --- | --- | --- |
| 6. | Variations in prices not taken into account while planning, will lead to cost overruns and delays of the project. | 34.5 | 43.6 | 14.5 | 7.3 | - |
| 7. | Deficiencies of cost estimates prepared will result in delays and cost overruns. | 30.0 | 52.7 | 5.5 | 9.1 | 2.7 |
| 8. | Escalation of material prices not taken in account during planning may lead to cost overruns resulting in project delays. | 29.1 | 53.6 | 10.0 | 4.5 | 2.7 |
| 9. | Discrepancies and / or deficiencies in contract documents may lead to project delays and cost overruns. | 29.1 | 46.4 | 12.7 | 10.0 | 1.8 |
| 10. | Unexpected weather / geological condition not taken into account while planning, will lead to delays and cost overruns. | 24.5 | 51.8 | 10.9 | 12.7 | - |
| 11. | Incomplete / delayed approvals will lead to cost overruns and delays. | 28.2 | 55.5 | 10.9 | 4.5 | 0.9 |

37

| 12. | Lack of coordination between Architect, Client, Consultant and Executing Agency during preparation of estimates and drawings will lead to delays and cost overruns in the project. | 26.4 | 53.6 | 14.5 | 5.5 | - |
| --- | --- | --- | --- | --- | --- | --- |

Table 4.3 Frequency distribution of Poor planning sub components
Source (Calculated by Researcher)

4.5 Insufficient Site Supervision

Literature has also highlighted that insufficient supervision at the site of project is another significant contributor for the delay and overrun cost. This factor has many dimensions as it was tried to cover it through almost 26 dimensions. Every dimension has got response on 5 point likert scale. These dimensions are poor leadership at site, poor supervision, timely non availability of material, poor quality of workmanship etc. results have shown that first dimension is about poor leadership at site; 40% respondents were strongly agreed, 51.8% were agree with this dimension. Very minute percentage is disagreed with this factor. It means it is an important delaying factor in construction projects. Poor supervision and management by the project management team has got maximum response in the category of strongly agree as compared to other dimensions; that is 42.7%. Similarly lack of corrective decisions at the site has got highest attention in the category of agree as its percentage is 64.5 which is highest response in this category. Almost ¼th of sample were undecided about that difficult site conditions and terrain may lead to cost overruns and delays in the project. Overall researcher can conclude that poor leadership; poor supervision at the site, timely non availability of material at the site are the most important reasons of delay at the site of construction projects. This factor (insufficient site supervision) is also important factor of delay in projects as not a single dimension out of 26 got any negative response from

38

respondents. Almost majority relied that all dimensions are causing delay and overrun cost in the projects.

| Sr. # | Questions | Strongly agree | Agree | Neutral | Disagree | Strongly disagree |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Poor leadership at site may cause cost overruns and delays in the project. | 40.0 | 51.8 | 3.6 | 4.5 | - |
| 2 | Poor supervision and management by the Project management team/ executing agency will lead to cost overruns and delays in the project. | 42.7 | 48.2 | 5.5 | 3.6 | - |
| 3 | Timely non-availability of material and equipment at site will lead to cost overruns and delays in the project. | 32.7 | 60.0 | 3.6 | 2.7 | .9 |
| 4 | Poor quality of workmanship will lead to cost overruns and delays in the project. | 26.4 | 55.5 | 10.9 | 7.3 | - |
| 5 | Lack of top management commitment will lead to cost overruns and delays in the project | 30.9 | 50.0 | 14.5 | 3.6 | .9 |
| 6 | Low management competency of sub-contractors will lead to cost overruns and delays in the project. | 27.3 | 51.8 | 12.7 | 8.2 | - |
| 7 | Shortage of human resources to handle project will lead to cost overruns and delays in the project. | 20.9 | 60.0 | 11.8 | 6.4 | .9 |
| 8 | Sub-contractors leaving without completing the project will lead to cost overruns and | 34.5 | 44.5 | 12.7 | 7.3 | .9 |

39

|  | delays in the project. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 9 | Inexperienced workforce/ non- technical personnel and staff turnover will lead to cost overruns and delays in the project. | 32.7 | 52.7 | 9.1 | 5.5 | - |
| 10 | Frequent design changes by the client / contractor during construction will lead to cost overruns and delays in the project. | 33.6 | 52.7 | 8.2 | 5.5 | - |
| 11 | Poor financial control on site will lead to cost overruns and delays in the project. | 31.8 | 59.1 | 6.4 | 2.7 | - |
| 12 | Delayed payments to supplier / sub-contractor will lead to cost overruns and delays in the project. | 26.4 | 53.6 | 10.0 | 7.3 | 2.7 |
| 13 | Contractual claims, such as extension of time with cost claims will lead to cost overruns and delays in the project. | 23.6 | 54.5 | 10.9 | 7.3 | 3.6 |
| 14 | Mistakes during construction will lead to cost overruns and delays in the project. | 25.5 | 54.5 | 11.8 | 8.2 | - |
| 15 | Frequent breakdown of construction and equipment will lead to cost overruns and delays in the project. | 23.6 | 57.3 | 12.7 | 6.4 | - |
| 16 | Labour shortages and strikes by site personnel will lead to cost overruns and delays in the project. | 20.9 | 61.8 | 13.6 | 3.6 | - |
| 17 | Delayed material procurement due to contractor’s financial difficulties will lead to | 37.3 | 50.0 | 11.8 | .9 | - |

40

|  | cost overruns and delays in the project. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 19 | Rework required due to poor work or the sub standard material by contractors may lead to cost overruns and delays in the project. | 30.0 | 50.9 | 13.6 | 5.5 | - |
| 20 | Poor schedule management and poor monitoring and control e.g. due to incompetent and/ or unreliable supervisors may lead to cost overruns and delays in the project. | 35.5 | 52.7 | 7.3 | 4.5 | - |
| 21 | Difficult site conditions and terrain may lead to cost overruns and delays in the project. | 17.3 | 46.4 | 25.5 | 10.9 | - |
| 22 | Contractors’ work load i.e. involved in so many projects at a time may lead to cost overruns and delays in the project. | 20.9 | 43.6 | 18.2 | 11.8 | 5.5 |
| 23 | Project management/ executing agency supervising multiple projects at same time will lead to cost overruns and delays in the project. | 19.1 | 41.8 | 20.0 | 17.3 | 1.8 |
| 24 | Occurrences of disputes at site will lead to cost overruns and delays in the project. | 12.7 | 59.1 | 16.4 | 11.8 | - |
| 25 | Change of local laws and political conditions may hinder the construction work resulting in delays and cost overruns in the project. | 26.4 | 57.3 | 8.2 | 4.5 | 3.6 |

| 26 | Lack of timely decisions and corrective actions by the project management team may | 23.6 | 64.5 | 8.2 | 3.6 | - |
| --- | --- | --- | --- | --- | --- | --- |

41

|  | cause cost overruns and delays in the project. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |

Table 4.4 Frequency distribution of insufficient supervision at site sub components

Source (Calculated by Researcher)

4.6 Lack of interdepartmental communication

Literature has identified that lack of coordination, harmonization and communication between different departments as one of the important cause of delay and overrun cost. This factor has been measured through 14 different dimensions. Dimensions for this factor are; Lack of coordination between all stakeholders, frequent changes of scope due to client’s influence, cumbersome approval procedures and delays in administrative Government Departments, Disagreement over some contract conditions etc. Results have depicted that respondents were strongly agreed that Poor cash flows to contractors, sub-contractors and suppliers and Hurdles by bureaucracy in approvals and release of funds are the main causes of delays and cost overrun under the subject and main factor of lack of interdepartmental communication. Public objections may cause overrun cost and delay has got highest percentage in the category of agree as its value is 64.5%. Respondents have also shown some disagreement like; High performance of quality expectation from client irrespective of practical conditions, Disagreement over some contract conditions. But this disagreement is not too much that it would be considered as non contributing dimension in the delay and overrun cost. Overall this factor is also an important factor of delay and overrun cost.

| Sr. # | Questions | Strongly agree | Agree | Neutral | Disagree | Strongly disagree |
| --- | --- | --- | --- | --- | --- | --- |

42

| 1 | Lack of coordination between all stakeholders during scope preparation may lead to cost overruns and delays in the project. | 25.5 | 58.2 | 7.3 | 6.4 | 2.7 |
| --- | --- | --- | --- | --- | --- | --- |
| 2 | Frequent changes of scope due to client’s influence without Project management teams’ consent during construction will lead to cost overruns and delays in the project. | 30.9 | 62.7 | 5.5 | .9 | - |
| 3 | Cumbersome approval procedures and delays in administrative Government Departments will lead to cost overruns and delays in the project. | 30.9 | 50.0 | 10.0 | 9.1 | - |
| 4 | Disagreement over some contract conditions may lead to cost overruns and delays in the project. | 13.6 | 60.0 | 12.7 | 10.9 | 2.7 |
| 5 | High performance of quality expectation from client irrespective of practical conditions may lead to cost overruns and delays in the project. | 14.5 | 50.0 | 21.8 | 10.9 | 2.7 |
| 6 | Delays in technical sanction by top management of Executing agency will lead to cost overruns and delays in the project. | 19.1 | 60.9 | 11.8 | 5.5 | 2.7 |
| 7 | Poor communication and slow responses to site queries will lead to cost overruns and delays in the project. | 23.6 | 59.1 | 9.1 | 8.2 | - |
| 8 | Poor cash flows to contractors, sub-contractors and suppliers will lead to cost overruns and delays in the project. | 33.6 | 46.4 | 13.6 | 5.5 | .9 |
| 9 | Hurdles by bureaucracy in approvals and release of funds may lead to cost overruns and | 33.6 | 52.7 | 8.2 | 5.5 | - |

43

|  | delays in project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 10 | Contradiction in construction documents will lead to cost overruns and delays in the project. | 20.9 | 55.5 | 15.5 | 7.3 | .9 |
| 11 | Inadequate terms and conditions including technical specifications in tender documents will lead to cost overruns and delays in the project. | 24.5 | 50.9 | 8.2 | 10.9 | 5.5 |
| 12 | New stakeholders emerge and initiate change request, will cause delays and cost overruns. | 24.5 | 52.7 | 10.9 | 7.3 | - |
| 13 | Public objections and their disturbance may cause cost overruns and delays in the project. | 17.3 | 64.5 | 13.6 | 3.6 | .9 |
| 14 | Misunderstandings and poor working relationships between stakeholders will cause cost overruns and delays in the project. | 23.6 | 63.6 | 8.2 | 4.5 | - |

Table 4.5 Frequency distribution of Lack of interdepartmental communication sub components

Source (Calculated by Researcher)

4.7 Correlation Analysis

Correlation is a term which is used to see the relationship between two or more quantitative variables. It has two types; Pearson and spearman correlation. Statistically when variable data is following the normal distribution then researcher uses Pearson correlation otherwise researcher has to use spearman correlation. In this study no variable has quantitative nature but researcher has developed indexes of these variables by adding the responses of each dimension of factor separately.  So to see the correlation between these three important factors researcher decided to apply this analysis. First of all normality

44

assumption was assessed through kolmogrove smirnove test. This test results have shown that the only one variable data has followed the assumption of normality that is lack of interdepartmental communication. But to apply the pearson correlation researcher has to follow the assumption that both variables have normal distribution. In this scenario spearman correlation was used.

| One-Sample Kolmogrove-Smirnov Test |  |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Poor planning | Insufficient site supervision | Lack of interdepartmental communication |
| N |  | 110 | 110 | 110 |
| Normal Parametersa | Mean | 20.63 | 51.79 | 28.84 |
|  | Std. Deviation | 5.595 | 12.560 | 8.213 |
| Most Extreme Differences | Absolute | .137 | .130 | .122 |
|  | Positive | .137 | .130 | .122 |
|  | Negative | -.074 | -.074 | -.079 |
| Kolmogorov-Smirnov Z |  | 1.438 | 1.361 | 1.283 |
| Asymp. Sig. (2-tailed) |  | .032 | .049 | .074 |

Table 4.6 Normality test for main three factors of study

Source (Calculated by Researcher)

After assessing the assumption through one sample K S test, a graph (scatter plot) has been formulated. It is just to see the graphical view of relationship. For this purpose scatter matrix was made. This graph has shown that all factors have positive correlation among them as there is increasing trend in all variables in straight line.

45

Figure 4.2 Correlation matrix

Source (Calculated by Researcher)

This table is about the spearman correlation analysis. This table has shown that all factors have strong correlation with each other. P-values of these relationships are significant at 0.05 level of significance. Insufficient supervision and lack of proper planning has relation with correlation coefficient 0.689 that is close to 0.7 which means very strong correlation exists between them. This relationship has (0.00) p value that is less than 0.05. Similarly other relationship can be seen in this table. Lack of interdepartmental communication and insufficient site supervision has highest relationship between them as r= 0.816**. ** shows that there is highly significant relationship between the studied variables.

46

| Correlations |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  | Poor planning | Insufficient site supervision | Lack of interdepartmental communication |
| Spearman's rho | Poor planning | Correlation Coefficient | 1.000 | .689** | .703** |
|  |  | Sig. (2-tailed) | . | .000 | .000 |
|  |  | N | 110 | 110 | 110 |
|  | Insufficient site supervision | Correlation Coefficient | .689** | 1.000 | .816** |
|  |  | Sig. (2-tailed) | .000 | . | .000 |
|  |  | N | 110 | 110 | 110 |
|  | Lack of interdepartmental communication | Correlation Coefficient | .703** | .816** | 1.000 |
|  |  | Sig. (2-tailed) | .000 | .000 | . |
|  |  | N | 110 | 110 | 110 |
| **. Correlation is significant at the 0.01 level (2-tailed). |  |  |  |  |  |

Table 4.7 Spearman Correlation analysis table

Source (Calculated by Researcher)

4.8 Severity index

Based on the response to the survey, a severity index was calculated to interpret the degree of seriousness effect of those problems. This index was calculated as follows (Babbie, 1989).

4.8.1Severity Index for Poor planning

This bar chart has shown the severity index for first factor that is poor planning. This factor further divides into 12 sub factors. This bar chart horizontal length explains the severity or contribution of this sub factor into delaying of public construction projects. This

47

chart of severity index depicts that poorly defined scope and inadequate planning are the highest contributing factor in delay and overrun cost. In other words researcher can say that these two sub factors are most occurring phenomenon in the Punjab public projects delay. Unexpected weather condition not considered during planning of project is the least occurred cause of delay.

Figure 4.3 Severity index bar chart for Poor planning sub components

Source (Made by Researcher)

4.8.2 Severity Index for Lack of insufficient site supervision

This chart has information about the lack of site supervision and its sub factors. This factor was measured through 26 sub parts. This graph as shown that poor supervision and management at site has got 90.75% severity index score. This sub part has got most frequently occurred position according to severity index. Project management supervising

48

multiple projects at same time as sub component of main factor is least important reason of delay according to respondents of  study.

Figure 4.4 severity index bar chart for insufficient supervision at site sub components

Source (Made by Researcher)

4.8.3 Severity Index for Lack of Interdepartmental Communication

This horizontal bar chart has the information about third component of study; lack of

interdepartmental communication. It has 14 sub components mentioned in the descriptive table and in this graph. This severity index chart has depicted that frequent changes in the

49

scope of project due to influence of clients is most occurred sub factor of main factor. Highperformance of quality expectation from client is the least severe sub component of delay and overrun cost.

Figure 4.5 severity index bar chart for Lack of interdepartmental communication sub components

Source (Made by Researcher)

4.8.4 Overall severity index for main factors

This graph has three horizontal bars; each bar for main factor; lack of interdepartmental communication, insufficient site supervision and poor planning. Poor planning has got

50

85.66% severity index value by averaging its sub factors. Insufficient site supervision has got 82.72% severity index value. It shows that lack of planning is the most frequently occurred reason of delay in the public sector projects in Punjab. Insufficient site supervision and lack of interdepartmental communication got second and third place according to severity index.

Figure 4.6 Severity index bar chart for all main components or factors

Source (Made by Researcher)

51

- Findings and Discussion

In this study a sample of 110 contractors, clients, project director and other categories were selected. Data was analyzed through SPSS (Statistical Package for Social Sciences) 19.0 version. Reliability analysis of collected data was performed through Cronbach’s Alpha. It is recommended that reliability value should be greater than 0.70. In this research there are three main components of delaying causes; insufficient supervision at site, poor planning, lack of interdepartmental communication. Individual reliability and overall reliability analysis was calculated and concluded that data was reliable in all aspects. As overall and individual constructs have reliability coefficient greater than 0.70. So overall data and constructs are reliable.

Frequency distribution was also computed for all qualitative variables in section of three main causes of delaying and overrun cost. Frequency distribution for each variable has been calculated. Results have shown that majority respondents and technical experts related to construction field are agreed that these three causes have strong impact on the overrun cost and delay in public projects. In the main construct of poor planning; first two dimensions (poor scope of project and planning) got maximum agreement of respondents as they said that they were strongly agreed with these two factors of delay and cost overrun.  On the other side other problems were also considered as important for delays but less than these two which have mentioned here. Similarly Poor supervision and management by the project management team got maximum response in the category of strongly agree as compared to other dimensions; that is 42.7%. Lack of corrective decisions at the site has got highest attention in the category of agree as its percentage is 64.5 which is highest response in this category. Almost 25% of sample was undecided about that difficult site conditions and terrain may lead to cost overruns and delays in the project. Overall researcher found that poor leadership; poor supervision at the site, timely non availability of material at the site are the

52

most important reasons of delay the site of construction projects. For the third factor of interdepartmental communication, results have depicted that respondents were strongly agreed that Poor cash flows to contractors, sub-contractors and suppliers and hurdles by bureaucracy in approvals and release of funds are the main reasons of delays and cost overrun under the subject and main factor of lack of interdepartmental communication. Public objections may cause overrun of cost and delay has got highest percentage in the category of

agree as its value is 64.5%. Respondents have also shown some disagreement like; High performance of quality expectation from client irrespective of practical conditions, Disagreement over some contract conditions. But overall this concept has strong influence on the overrun cost and delay of public construction projects.

Correlation among these three main concepts was also computed through spearman correlation. Kolmogrove smirnove test was also used to check the assumption of normality. This test results have shown that data except lack of departmental communication had non-normal distribution. This test of relationship has shown that all variables have strong positive relationship with each other. All the correlation coefficients have values greater than equal to 0.70. It means that variables have strong relationship with each other. As literature has suggested that correlation coefficient greater than 0.7 means strong correlation value. Positive correlation means if there is chance increase in value or score of one factor other factor will also be increased and vice versa.

Severity index was calculated at two stages; individual variable (52 sub factors of study) and overall factors (3 factors). Through these results researcher found that poorly defined scope,  inadequate planning, poor supervision and management at site, frequent changes in the scope of project due to influence of clients are most occurred reasons of delay 												53

and overrun cost. Overall poor planning is the most important reason of delay in this study as highlighted in the literature. Insufficient site supervision and lack of interdepartmental communication got second and third position with respect to severity index.

54

- Conclusion

Construction project is very essential part of infrastructural development. Further this type of development is logically most important part of communication, transportation and overall development of country. Developed and developing both nations have to face delays and overrun of cost in the construction projects as literature indicated. But developing nations are not in the position to face such prolonged issues. Therefore solutions of these delaying causes and costs should be identified, so that their solutions can be provided.

In this study it was tried to explore the intensity or severity index of the main three factors of delay. These factors are lack of proper planning, poor site supervision and lack of interdepartmental communication. First of all on the basis of these findings it was confirmed through description of variables (52 variables) that all these factors have their role in the delay and overrun cost. It was suggested on the basis of agreement of respondents on the statements given in the questionnaire which was formulated on the basis of literature and previous findings.  Further these three components have many dimensions and each dimension has been ranked according to severity index.

On the basis of this study finding researcher can conclude that poor planning is the most important reason and factor of delay in practical scenario. It is said that plan is nothing but the planning is everything.  This study has highlighted that planning is not up to the mark in public sector projects of Punjab. Scope of the project is the basic element of the any project but this study has shown that this component is missing or lacking in majority public projects. Similarly inadequate planning is another component which is according to scope of project. Its lacking also creates problems of delay and overrun cost. It is also concluded that poor planning is the most frequently occurring reason of delay according to contractors, projects

55

directors, monitoring and evaluation team, clients and other categories as well. Site supervision is important part at the time of execution. But lacking of this part creates many problems and hindrance for the execution team. These problems then delay the projects and create overrun cost. Lack of Interdepartmental communications among different government departments, clients, contractors and other stakeholders got third position according to severity index which cause delay in the projects and overrun cost.

  - Recommendations

On the basis of this study following are few recommendations for the contactors, government and policy makers’ that

- Special training and seminars need to be conducted by the government for the bidders and interested contractors for the better understanding of scope and vision of the projects which further guide them for planning accordingly.

- In order to improve contractors’ managerial skills there is need for continuous work-training programs for personnel in the industry to update their knowledge and be familiar with project management techniques and processes which reduce the overrun cost and delay of projects.

- Government should make policies to improve the planning skills and interdepartmental harmonization so that delaying issues can be controlled at governmental and funding agency level.

- Government must make strong Monitoring and evaluation units to improve the execution plans and site supervision of projects especially planning, scheduling, time and cost control, and the information systems of the bidders

56

  - Limitations of Study

Every research needs some type of improvement in practical scenarios. It means there is always some limitation of every research and findings regarding its generalization. This study also has few limitations

- Time is the main limitation in this research. This research can be conducted at broader level to explore the processes of delays and hidden factors behind them. Due to shortage of time it could not be explored.

- This project might be specific to construction projects so its findings can be generalized to this sector. Because other sectors and their projects might have some other factors behind delays and overrun cost.

57

References

Abd El-Razek, M., Bassioni, H., & Mobarak, A. (2008). Causes of delay in building construction projects in Egypt. Journal of construction engineering and management, 134(11), 831-841.

Abdullah, M. R., Abdul Rahman, I., Azis, A., & Asmi, A. (2009). Delay in large MARA construction projects based on project management consultant perspective.

Ahmed, S. M., Azhar, S., Castillo, M., & Kappagantula, P. (2002). Construction delays in Florida: An empirical study. Paper presented at the ASC ANNUAL CONFERENCE.

Akinsola, A. (1996). Neural network model for predicting building projects’ contingency. Paper presented at the Conference: proceedings of association of researchers in construction management, ARCOM.

Al-Khalil, M. I., & Al-Ghafly, M. A. (1999). Important causes of delay in public utility projects in Saudi Arabia. Construction Management & Economics, 17(5), 647-655.

Al-Momani, A. H. (2000). Construction delay: a quantitative analysis. International journal of project management, 18(1), 51-59.

Al‐Kharashi, A., & Skitmore, M. (2009). Causes of delays in Saudi Arabian public sector construction projects. Construction Management and Economics, 27(1), 3-23.

Alaghbari, W. e., Razali A. Kadir, M., Salim, A., & Ernawati. (2007). The significant factors causing delay of building construction projects in Malaysia. Engineering, Construction and Architectural Management, 14(2), 192-206.

Ali, A., & Kamaruzzaman, S. (2010). Cost performance for building construction projects in Klang valley. Journal of Building performance, 1(1).

Alkass, S., Mazerolle, M., & Harris, F. (1996). Construction delay analysis techniques. Construction Management & Economics, 14(5), 375-394.

Ameh, O. J., Soyingbe, A. A., & Odusami, K. T. (2010). Significant factors causing cost overruns in telecommunication projects in Nigeria. Journal of Construction in Developing Countries, 15(2), 49-67.

Apolot, R., Alinaitwe, H., & Tindiwensi, D. (2011). An investigation into the causes of delay and cost overrun in Uganda’s public sector construction projects. Paper presented at the Second International Conference on Advances in Engineering and Technology.

Assaf, S. A., & Al-Hejji, S. (2006). Causes of delay in large construction projects. International journal of project management, 24(4), 349-357.

58

Assaf, S. A., Al-Khalil, M., & Al-Hazmi, M. (1995). Causes of delay in large building construction projects. Journal of management in engineering, 11(2), 45-50.

Ayman Othman, A., & El-Gendawy, A. H. S. (2012). Public-private partnership for lean sustainable development in construction. Journal of Construction Project Management and Innovation, 2(2), 377-402.

Ayudhya, B. I. N. (2011). Evaluation of common delay causes of construction projects in Singapore. Journal of Civil Engineering and Architecture, 5(11).

Babbie, E. R. (1989). The practice of social research: Wadsworth Publishing Company.

Car-Pušić, D. (2010). Contracted price overrun as contracted construction time overrun function. Tehnički vjesnik: znanstveno-stručni časopis tehničkih fakulteta Sveučilišta u Osijeku, 17(1), 23-29.

Chan, D. W., & Kumaraswamy, M. M. (1997). A comparative study of causes of time overruns in Hong Kong construction projects. International journal of project management, 15(1), 55-63.

Charoenngam, C., & Sriprasert, E. (2001). Assessment of cost control systems: a case study of Thai construction organizations. Engineering Construction and Architectural Management, 8(5‐6), 368-380.

Cohen, B. (2006). Urbanization in developing countries: Current trends, future projections,

and key challenges for sustainability. Technology in society, 28(1), 63-80.

De Wit, A. (1988). Measurement of project success. International journal of project management, 6(3), 164-170.

Doloi, H., Sawhney, A., Iyer, K., & Rentala, S. (2012). Analysing factors affecting delays in Indian construction projects. International journal of project management, 30(4), 479-489.

Emam, H., Farrell, P., & Abdelaal, M. (2015) CAUSES OF DELAY ON INFRASTRUCTURE PROJECTS IN QATAR.

Faridi, A. S., & El‐Sayegh, S. M. (2006). Significant factors causing delay in the UAE construction industry. Construction Management and Economics, 24(11), 1167-1176.

Field, B., & Ofori, G. (1988). Construction and economic development. A case study.

Flanagan, R., Norman, G., Ireland, V., & Ormerod, R. (1986). A fresh look at the UK and US construction industry. UK: Building Employers Confederation.

Flyvbjerg, B., Bruzelius, N., & Rothengatter, W. (2003). Megaprojects and risk: An anatomy of ambition: Cambridge University Press.

59

Flyvbjerg, B., Skamris Holm, M. K., & Buhl, S. L. (2003). How common and how large are cost overruns in transport infrastructure projects? Transport reviews, 23(1), 71-88.

Frimpong, Y., Oluwoye, J., & Crawford, L. (2003). Causes of delay and cost overruns in construction of groundwater projects in a developing countries; Ghana as a case study. International journal of project management, 21(5), 321-326.

Guide, A. (2001). Project Management Body of Knowledge (PMBOK® GUIDE). Paper presented at the Project Management Institute.

Han, S. H., Yun, S., Kim, H., Kwak, Y. H., Park, H. K., & Lee, S. H. (2009). Analyzing schedule delay of mega project: Lessons learned from Korea train express. Engineering Management, IEEE Transactions on, 56(2), 243-256.

Haseeb, M., Bibi, A., & Rabbani, W. (2011). Problems of projects and effects of delays in the construction industry of Pakistan. Australian Journal of Business and Management Research, 1(5), 41-50.

Haseeb, M., Lu, X., Hoosen, A. B., & Rabbani, W. (2011). Causes and effects of delays in large construction projects of pakistan. Kuwait Chapter of Arabian Journal of Business and Management Review, 1(4), 18-42.

Kaliba, C., Muya, M., & Mumba, K. (2009). Cost escalation and schedule delays in road

construction projects in Zambia. International journal of project management, 27(5), 522-531.

Kaming, P. F., Olomolaiye, P. O., Holt, G. D., & Harris, F. C. (1997). Factors influencing construction time and cost overruns on high-rise projects in Indonesia. Construction Management & Economics, 15(1), 83-94.

Kumar, R. (1999). Research Methodology: A step-by-step approach: London: Sage Publications.

Latham, M. (1994). Constructing the team, Final report of the joint government/industry review of procurement and contractual arrangements in the United Kingdom construction industry: HMSO, London.

Lee, J.-K. (2008). Cost overrun and cause in Korean social overhead capital projects: Roads, rails, airports, and ports. Journal of Urban Planning and Development, 134(2), 59-62.

Ling, F. Y. Y., & Hoi, L. (2006). Risks faced by Singapore firms when undertaking construction projects in India. International journal of project management, 24(3), 261-270.

60

Lo, T. Y., Fung, I. W., & Tung, K. C. (2006). Construction delays in Hong Kong civil engineering projects. Journal of construction engineering and management, 132(6), 636-649.

Long, N. D., Ogunlana, S., Quang, T., & Lam, K. C. (2004). Large construction projects in developing countries: a case study from Vietnam. International journal of project management, 22(7), 553-561.

Mahamid, I. (2011). Risk matrix for factors affecting time delay in road construction projects: owners' perspective. Engineering, Construction and Architectural Management, 18(6), 609-617.

Mansfield, N. R., Ugwu, O., & Doran, T. (1994). Causes of delay and cost overruns in Nigerian construction projects. International journal of project management, 12(4), 254-260.

Marzouk, M. M., & El-Rasas, T. I. (2014). Analyzing delay causes in Egyptian construction projects. Journal of advanced research, 5(1), 49-55.

Mthalane, D., Othman, A., & Pearl, R. (2008). The economic and social impacts of site accidents on the South African society. Paper presented at the proceedings of the 5th post graduate conference on construction industry development.

Nawaz, T., Ikram, A. A., & Qureshi, A. A. (1985). Causes of Schedule Overruns in Pakistani

Construction Industry. Journal of Heat and Mass Transfer, 28, 1019-1030.

Nkado, R. N. (1995). Construction time-influencing factors: the contractor's perspective. Construction Management and Economics, 13(1), 81-89.

O'Brien, J. J. (1976). Construction Delay: Responsibilities, Risks, and Litigation: Cahners Books International.

Odeh, A. M., & Battaineh, H. T. (2002). Causes of construction delay: traditional contracts. International journal of project management, 20(1), 67-73.

Okpala, D. C., & Aniekwu, A. N. (1988). Causes of high costs of construction in Nigeria. Journal of construction engineering and management, 114(2), 233-244.

Olawale, Y. A., & Sun, M. (2010). Cost and time control of construction projects: inhibiting factors and mitigating measures in practice. Construction Management and Economics, 28(5), 509-526.

Pickavance, K. (2000). Delay and disruption in construction contracts: LLP.

Sambasivan, M., & Soon, Y. W. (2007). Causes and effects of delays in Malaysian construction industry. International journal of project management, 25(5), 517-526.

61

Shore, B., & Cross, B. J. (2005). Exploring the role of national culture in the management of large-scale international science projects. International journal of project management, 23(1), 55-64.

Sturup, S. (2009). Megaprojects and Governability. World Academy of Science, Engineering and Technology, 54.

Yamane, T. (1967). Elementary sampling theory.

Yang, J.-B., & Chen, C.-C. (2015). Causes of Budget Changes in Building Construction Projects: An Empirical Study in Taiwan. The Engineering Economist, 60(1), 1-21.

Zeybek, H., & Kaynak, M. (2008). Role of mega projects in sustainable urban transport in developing countries: The case of Istanbul Marmaray Project. Proceedings of Codatu XIII: Sustainable Development Challenges of Transport in Cities of the Developing World: Doing what works, 12-14.

Zikmund, W., Babin, B., Carr, J., & Griffin, M. (2012). Business research methods: Cengage Learning.

62

Appendix

# QUESTIONNAIRE FOR DELAYS AND COST OVERRUNS IN PUBLIC SECTOR BUILDING PROJECTS

Please enter the Demographic Information requested in the form below. Your name, the name of your organization/department and your contact details will be kept strictly confidential. Summaries and statistical analyses of responses will be presented to the University.

| Name |  |
| --- | --- |
| Designation |  |

Please tick (√) the relevant option:

|  | Consultant | Client | Project Director / Manager | Monitoring & Evaluation Officer | Contractor | Any other |
| --- | --- | --- | --- | --- | --- | --- |

| Company / Department |  |
| --- | --- |

| Email Address |  |
| --- | --- |

(Pl encircle       or tick  (√) the options)

Poor planning

| Sr. # | Questions | Strongly Disagree |  |  | Disagree | Neutral | Agree |  | Strongly agree |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Poorly defined scope would cause time delay and cost overruns in the projects. | 1 |  |  | 2 | 3 |  | 4 | 5 |
| 2. | Inadequate planning will lead to delays and cost over runs in the project. | 1 |  | 2 |  | 3 |  | 4 | 5 |
| 3. | The confusing and ambiguous requirements by the client will cause delays and cost overruns in the project. | 1 | 2 |  |  | 3 |  | 4 | 5 |
| 4. | The improper feasibility study provided by the client would result in delay and cost overruns of the project. | 1 | 2 |  |  | 3 |  | 4 | 5 |
| 5. | Unclear project objectives by the client will lead to delay and cost overruns of the project. | 1 | 2 |  |  | 3 |  | 4 | 5 |
| 6. | Variations in prices not taken into account while planning, will lead to cost overruns and delays of the project. | 1 | 2 |  |  | 3 |  | 4 | 5 |
| 7. | Deficiencies of cost estimates prepared will result in delays and cost overruns. | 1 | 2 |  |  | 3 |  | 4 | 5 |
| 8. | Escalation of material prices not taken in account during planning may lead to cost overruns resulting In project delays. | 1 | 2 |  |  | 3 |  | 4 | 5 |

63

9. Discrepancies and / or deficiencies in contract 1 2 3 4 5 documents may lead to project delays and cost overruns.

10. Unexpected weather / geological condition not 1 2 3 4 5 taken into account while planning, will lead to delays and cost overruns.

11. Incomplete / delayed approvals will lead to cost 1 2 3 4 5 overruns and delays.

12. Lack of coordination between Architect, client, 1 2 3 4 5 Consultant and Executing Agency during Preparation of estimates and drawings will lead to Delays and cost overruns in the project.

Insufficient site supervision

| Sr. # | Questions | Strongly Disagree | Disagree | Neutral | Agree | Strongly agree |
| --- | --- | --- | --- | --- | --- | --- |
| 13. | Poor leadership at site may cause cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 14. | Poor supervision and management by the Project management team/ executing agency will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 15. | Timely non-availability of material and equipment at site will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 16. | Poor quality of workmanship will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 17. | Lack of top management commitment will lead to cost overruns and delays in the project | 1 | 2 | 3 | 4 | 5 |
| 18. | Low management competency of sub-contractors will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 19. | Shortage of human resources to handle project will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 20. | Sub-contractors leaving without completing the project will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 21. | Inexperienced workforce/ non- technical personnel and staff turnover will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 22. | Frequent design changes by the client / contractor during construction will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 23. | Poor financial control on site will lead to cost | 1 | 2 | 3 | 4 | 5 |

64

|  | Overruns and delays in the projects. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 24. | Delayed payments to supplier / sub-contractor Will lead to cost overruns and delays in the project | 1 | 2 | 3 | 4 | 5 |
|  |  | Strongly Disagree | Disagree | Natural | Agree | Strongly agree |
| 25. | Contractual claims, such as extension of time With cost claims will lead to cost overruns and Delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 26. | Mistakes during construction will leave to cost Overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 27. | Frequent breakdown of construction and equipment will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 28. | Labour shortages and strikes by site personnel will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 29. | Delayed material procurement due to contractor’s financial difficulties will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 30. | Slow decision making by the site management will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 31. | Rework required due to poor work or the sub standard material by contractors may lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 32. | Poor schedule management and poor monitoring and control e.g. due to incompetent and/ or unreliable supervisors may lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 33. | Difficult site conditions and terrain may lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 34. | Contractors’ work load i.e. involved in so many projects at a time may lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 35. | Project management/ executing agency supervising multiple projects at same time will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 36. | Occurrences of disputes at site will lead to cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |
| 37. | Change of local laws and political conditions may hinder the construction work resulting in delays and cost overruns in the project. | 1 | 2 | 3 | 4 | 5 |
| 38. | Lack of timely decisions and corrective actions by the project management team may cause cost overruns and delays in the project. | 1 | 2 | 3 | 4 | 5 |

65

Lack of interdepartmental  communication

| Sr. # | Questions | Strongly Disagree |  | Disagree |  | Neutral | Agree | Strongly agree |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 39. | Lack of coordination between all stakeholders during scope preparation may lead to cost overruns and delays in the project. | 1 |  | 2 |  | 3 | 4 | 5 |
| 40. | Frequent changes of scope due to client’s influence without Project management teams’ consent during construction will lead to cost overruns and delays in the project. | 1 |  | 2 |  | 3 | 4 | 5 |
| 41. | Cumbersome approval procedures and delays in administrative Government Departments will lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 42. | Disagreement over some contract conditions may lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 43. | High performance of quality expectation from client irrespective of practical conditions may lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 44. | Delays in technical sanction by top management of Executing agency will lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 45. | Poor communication and slow responses to site queries will lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 46. | Poor cash flows to contractors, sub-contractors and suppliers will lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 47. | Hurdles by bureaucracy in approvals and release of funds may lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 48. | Contradiction in construction documents will lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 49. | Inadequate terms and conditions including technical specifications in tender documents will lead to cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 50. | New stakeholders emerge and initiate change request, will cause delays and cost overruns. |  | 1 |  | 2 | 3 | 4 | 5 |
| 51. | Public objections and their disturbance may cause cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |
| 52. | Misunderstandings and poor working relationships between stakeholders will cause cost overruns and delays in the project. |  | 1 |  | 2 | 3 | 4 | 5 |

- Thanks for giving your precious time and for your cooperation.

66