AN EMPIRICAL ASSESSMENT OF THE FACTORS CAUSING DELAYS IN PROJECT COMPLETION IN THE CONSTRUCTION SECTOR OF LAHORE PAKISTAN

NAME: Laraib Fatima                                            ENROLLMENT: 03-298182-063

SEMESTER: Fall-2019, MSPM – III                 PROGRAM: MS Project Management

DEPARTMENT OF MANAGEMENT SCIENCES

BAHRIA UNIVERSITY LAHORE CAMPUS

RESEARCH THESIS

Principal Supervisor: Dr. Saif- Ul – Haq

Copyright

This copy of the thesis has been supplied on condition that anyone who consults it is understood to recognize that its copyright rests with the author and that no information from this thesis and no information derived from it may be published without author's prior consent.

© Laraib Fatima (2019-2020)

# SUBMISSION FORM OF THESIS

Candidate Name: Laraib Fatima

I have submitted four copies of thesis for examination for the degree of MSPM.

Thesis Titled: AN EMPIRICAL ASSESSMENT OF THE FACTORS CAUSING DELAYS IN PROJECT COMPLETION IN THE CONSTRUCTION SECTOR OF LAHORE PAKISTAN

Candidate Signature: 	 Date:

Certificate of Principal Supervisor

I, Dr Saif-Ul-Haq, being the Principal Supervisor for the above student, certify that thesis is in a form suitable for examination, and the candidate has perused his course following the Rules of the University.

Signature: 	 Date:

Recommendation of Examination

I recommend that the thesis be examined.

Principal Supervisor:	Date:

Co-Supervisor:	Date:

Not Recommendation of Examination

I recommend that the thesis may not be examined.

Principal Supervisor:	Date:

Co-Supervisor:	Date:

Statement by the Head Faculty/Department

I support the submission of the thesis of the student named above for examination under the University Rules for higher degrees.

Signature:	Date:

# BAHRIA UNIVERSITY, LAHORE

# Approval Sheet Submission for Higher Research Degree Thesis

Candidate Name: 			Laraib Fatima

Discipline: 				Project Management

Faculty/Department: 			Department of Management Sciences

I as a result of this certify that the above candidate's work, including the thesis, has been completed to my satisfaction and that the thesis is in a format and of an editorial standard recognized by the faculty/department as appropriate for examination.

Signature:

Principal Supervisor: Dr. Saif-Ul-Haq

Dated:

The undersigned certifies that a pre-completion seminar, and overview and synthesis of significant findings of the thesis, and the research is of a standard and extent appropriate for submission.

I have checked the candidate's thesis and the faculty/department recognizes its scope, format, editorial standards as appropriate.

Dean/Head of Faculty/Department

Dated:

# Declaration of Authentication

I, Laraib Fatima, Student in the Department of Management Sciences, Bahria University, Lahore Campus, certify that the research work presented in the thesis is to the best of my knowledge, my own. All resources used and help received in the preparation of this dissertation have been acknowledged. I hereby declare that I have not submitted this material, either in whole or in part, for any other degree at this or other institution.

Laraib Fatima

Acknowledgement

First and foremost, I would like to thank ALLAH ALMIGHTY for giving me the strength, knowledge, ability, and opportunity to undertake this research study and to persevere and complete it satisfactorily. Without his blessings, this achievement would not have been possible. Foremost, I would like to express my sincere gratitude to my advisors Dr. Saif-ul-Haq and M. Ahsan Chughtai for their continuous support and their constant guidance. Without their presence, it would have been challenging for me to complete my master’s study and research. Their suggestion was a continuous source to enlighten my way to reach the point of completing this degree on a high.

- Table of Contents

Abstract	11

1.	Introduction	13

1.1.	Background of the Study	13

1.2.	Literature Gap	14

1.3.	Problem Statement	14

1.4.	The objective of the Study	15

1.5.	Research Question	15

1.6.	Significance of the study	15

1.7.	Organization of the Thesis	16

1.8.	Summary	17

2.	Literature Review	19

2.1.	Introduction	19

2.2.	Definition of the variables	19

2.2.1.	The Contractor	19

2.2.2.	The Consultant	20

2.2.3.	The Client	23

2.2.4.	Enterprise External Factors	24

2.2.5.	Organizational Process Assets	25

2.2.6.	Project Manager Level of Autonomy	27

2.2.7.	Project Location	28

2.3.	Hypothesized Research Model	29

2.4.	Summary	30

3.	Research Design	32

3.1.	Population & Sampling Technique	32

3.2.	Measurement and Instrumentation	33

3.3.	Variables used	34

3.4.	Data Collection Procedure	35

3.5.	Demographics	35

3.6.	Data Analysis Technique	35

3.7.	Summary	36

4.	Introduction	38

4.1.	Demographics	38

4.1.1.	Sample Composition by Organization	38

4.1.2.	Position Demographics:	38

4.1.3.	Projects	39

4.1.4.	Experience Demographics	39

4.1.5.	Some projects completed:	40

4.2.	Variables Understudy	40

4.3.	Reliability	41

4.4.	Average Variance Extracted (AVE)	42

4.5.	Descriptive Analysis	43

4.5.1.	Contractor’s Incompetency	44

4.5.2.	Client’s Incompetency	47

4.5.3.	Consultant’s Incompetency	50

4.5.4.	EEFs	53

4.5.5.	OPAs	56

4.5.6.	Project Manager Autonomy	59

4.5.7.	Project Location	62

4.6.	Path Coefficients	66

5.	Conclusion, Discussion, Limitations and Future Research Suggestion	71

5.1.	Discussion	71

5.2.	Conclusion	75

5.3.	Limitations	75

5.4.	Future Recommendations	76

References	77

Appendix	83

Appendix: A Questionnaire	83

List of Tables

Table 1 Organizational Demographics	38

Table 2: Position Demographics	38

Table 3: Types of Projects Demographics	39

Table 4: Experience	39

Table 5: No of Projects	40

Table 6 Cornbrash’s Alpha Interpretation	41

Table 7 Cronbach’s Alpha Analysis (Individual)	41

Table 8 AVE	43

Table 9 Site Management issues	44

Table 10 Improper Construction Method	44

Table 11 Improper Planning	44

Table 12 Mistakes during construction stage	45

Table 13 Inadequate contractor experience	45

Table 14 Contractor's Incompetency Mean	47

Table 15 Finances and payment of completed work	47

Table 16 Owner interference	47

Table 17 Unrealistic contract duration and requirement imposed by the client	48

Table 18 Slow decision making	48

Table 19 Client's Incompetency Mean	49

Table 20 Delay in approving or preparation of shop drawings by the consultant	50

Table 21 Poor contract management	50

Table 22 Lack of Quality assurance and control	51

Table 23 Delay in approval of tests and inspection	51

Table 24 Consultant's Incompetency Mean	52

Table 25 Weather conditions	53

Table 26 Regulatory Changes	53

Table 27 Problem With neighbors	54

Table 28 Unforeseen ground conditions	54

Table 29 EEFs Mean	55

Table 30 Financial rewards (salary, bonus, and perquisite)	56

Table 31 Price increases of salary raises performance of the employee	56

Table 32 Benefits such as rent, clothing or fuel	57

Table 33 Bonuses given on special days	57

Table 34 OPA Mean	58

Table 35 The project Manager could freely choose tolls and technologies	59

Table 36 The project Manager had control over what he was supposed to accomplish	59

Table 37 The project Manager was granted autonomy on how to handle all requirements and changes	60

Table 38 The project Manager was free to assign personnel to the Project	60

Table 39 project Manager Level of Autonomy	62

Table 40 Restricted access at site	62

Table 41 Extreme weather conditions	63

Table 42 Slow decisions from owner	63

Table 43 Delay in material delivery by vendors	63

Table 44 Site accidents due to negligence	64

Table 45 Site accidents due to lack of safety measures	64

Table 46 Unforeseen ground conditions	64

Table 47 Hostile political conditions	65

Table 48 Inaccurate specification of site condition	65

Table 49 Project Location Mean	66

Table 60 Significance Testing Results of the Structural Model Path Coefficients	66

List of Figures

Figure 1 Organization of Thesis	17

Figure 2 Hypothesized Research Model	30

Figure 3 Sample Size Formula	32

Figure 4 Sampling Technique for data collection	33

Figure 5 Data Analysis Techniques	36

# Abstract

The purpose or focus of the study was to assess the factors which are causing a delay in project completion in the construction industry of Lahore Pakistan and investigating the effect of these delays. Also, the study was focused on seeing that either project manager level of autonomy and favourable project location do have any impact in minimizing the delays or not. For carrying out this study, 200 samples were obtained by a well-structured questionnaire from stakeholders connected with construction industry such as owners, consulting firms, contracting firms which were selected n random basis. PLS & SPSS software had been used for analysing the data to obtain the measurement models. The findings of the study showed that factors related to consultants had the significant impact in delaying the construction projects which is followed by clients related delays and then there comes delay caused by the contracting firms. Additionally, it has been observed that the project manager level of autonomy helps in minimizing the delays in construction projects. On the other hand, favourable project location cannot do so. The main limitation of the study was that it only covers the construction projects from selected one city. For this purpose, future studies can be extended to other cities or regions as well.

Keywords: Client’s incompetency, Consultant’s incompetency, Contractor’s incompetency, Enterprise Environment Factors, Organizational Process Assets, PLS, SPSS, Impact of Delay in Construction Projects.

# CHAPTER NO: 1

# INTRODUCTION

# Introduction

## Background of the Study

During the implementation of construction projects, the delay has proven to be one of the significant challenges faced by the project manager, and the primary reason is the hindrances in the completion of the project activities delaying their completion in comparison to the planned dates. Many of the construction projects in Pakistan have been facing delays (Aziz, 2018). These delays in the projects negatively affect the market image and prestige of the construction company, the owners, and the consultancy firms involved in these projects can cause financial losses for these organizations. There have been a few similar pieces of research such as (Iman Suleiman Al Maktoum, 2020), have been conducted in various developing countries and those researches have been studied to move forward with this research.

Several similar studies from developing countries have been reviewed, and a survey has been conducted for data collection from the different public organizations of Pakistan (Ullah, Thaheem, Siddiqui, & Khurshid, 2017). The analysis of the collected data points out the significant causes of delay in the construction projects in Pakistan as; ineffective planning and scheduling of a project by the contractor, delay in progress payments by the client, poor management at site and inadequate supervision of the contractors by the respective consultant and client, financial difficulties faced by the contractor, inadequate controlling and monitoring by the client and the consultant, non-availability of experienced and skilful technical staff mobilized by the contractor, late in completing the review and approval of the design documents by the consultant or the client, lack of proper and effective coordination and communication between the parties, delay in delivery of materials to the site, insufficient contractor experience, increase in political influences and the intervention by the warlords (Eik-Andresen, Landmark, Hajikazemi, Johansen, & Andersen, 2016). Finally, this thesis provides applicable recommendations to minimize or eliminate the causes of delays in construction projects in Pakistan.

In the projects specifically in the construction industry when even a single activity is delayed; it causes disturbance within the whole construction process. Various government projects in Pakistan are a perfect example of how the delay in the construction activity of the project can leads to negative reviews about it among the public. (Asmi, Djamaris, & Ihsan, 2019). Construction projects in Pakistan face delays, not of months but years due to inefficiency of government, and official administrators. There is a dire need for researches to be done to find the reasons and effects of the project delays within the construction industry in Pakistan; the analysis should be there. These analyses would help with identifying reasons behind delay and room for improvement. (Haseeb, Bibi, & Rabbani, 2011).

## Literature Gap

Similarly, to the previous research, this research will include the geographic boundaries of Pakistan Country, the experience of the Project managers on the construction sites in Pakistan, the project management techniques, and tools that are used by these project managers (Ali, Iqbal, & Iqbal, 2020). What makes this research a necessity in this field is that unlike other studies, it will include both the Organizational Process Assets (or OPAs) and External Environmental Factors (or EEFs). At the same time, this research will also consider whether there is an effect of the company’s reputation on the timely completion of the projects, while also considering the disputes. These claims took place within the project (Maqsoom, Choudhry, Umer, & Mehmood, 2019). The gap that this research will attempt to fill is that in this research we will convert the level of autonomy of the project managers and the location of the project into the study as the moderator variables that will be analyzed through the quantitative method. (Sambasivan, Deepak, Salim, & Ponniah, 2017).

## Problem Statement

In 2017, the Public Accounts Committee stated that more than 1,000 of the federally financed projects, amounting up to 7.9 trillion rupees, had been delayed due to various factors, out of which 2.231 trillion rupees had already been spent, That notes that the federal government has faced an opportunity cost of almost 2.231 trillion rupees due to such delays (Ali, Iqbal, & Iqbal, 2020), and that is only for public projects that exclude provincially funded projects that have faced delays and also not including private projects that have had to face delays due to different factors (Gamil, & Rahman, 2017). So the main focus of this research is to address one of the significant issues faced by the organizations during the execution of their projects, which is the delays in the construction projects that cause the success rate of the projects to reduce, heavily costing all the involved parties, which can be seen from the previous major projects in Pakistan that were initiated during the last decade. (Maqsoom, Choudhry, Umer, & Mehmood, 2019).

## The objective of the Study

The overall objective of this research is to identify the major causes for the delays in the construction projects so that the research could help the project managers and other decision-makers to prepare a strategy to eradicate those reasons for the delays. The specific objectives of the study are:

- Measuring the effects of consultant, client/owner, contractor, OPAs & EEFs (Govt policies, political and legal environment, and weather conditions) related factors in delaying the projects of construction industry of Lahore, Pakistan.

- To analyses the moderating effect of Project Manager level of autonomy and favorable project location on OPAs & EEFs respectively in delays of construction projects in Lahore, Pakistan.

## Research Question

The research questions developed for this study are mentioned as follows:

- Does client, consultant, contractor, EEFs, and OPAs related delays affect the completion of construction projects in Lahore, Pakistan?

- Does Project Manager Autonomy effectively moderate the relationship between OPAs and delays of construction projects in Lahore Pakistan?

- Does Project Location effectively moderate the relationship between EEFs and delays of construction projects in Lahore Pakistan?

## Significance of the study

The construction industry is considered the most significant one in overall sectors in Pakistan, majorly due to the employment opportunities it presents, which helps in increasing the GDP and economy of the country (Sohu, & Chandio, 2019). From the reviews of the few major projects in Pakistan, there have been significant delays in most of these projects (Sheikh, Ikram, Ahmad, Qadeer, & Nawaz, 2019). Delays mean late output due to the inefficiency of the contractor since procedures become complicated due to limited resources. The profit lost by the owner and the contractors, therefore, is equal to the opportunity cost of the projects missed. According to the contractor, if the price of bidding is low, only then a project can be won and while bidding the on low rates, no focus on quality and delays in construction time affect overall performance. So, it can be said that a delay in the project is one of the primary reasons for the failure of the projects and the loss of income for the owners, constructors, and contractors. (Zidane & Andersen, 2018).

This research has a higher level of significance that helps in identifying the causes of the delays in the construction projects and helps in finding out the reasons and factors that cause the delays in the construction projects within Pakistan. This research will increase the awareness of the possible problems which may result from Delays so that the organizations related to construction projects would prepare their strategies accordingly to reduce the delays in their projects. These aspects of the research help in making this research a significant one and making it worth the required efforts (Alofi, Kashiwagi, & Kashiwagi, 2016).

## Organization of the Thesis

This thesis consists of five chapters which are organized as follows:

This is studying the reasons for the project delays in the construction industry and the effects of the project delay on the involved organizations. To provide helpful and detailed insight to the readers, this research report is divided into different chapters. The thesis starts with an abstract that contains a summary of the fundamental research.

The first chapter contains the introduction of the research paper. It describes the background of the research, the gap in the existing literature, the problem statement of the study, the research questions that will be analyzed and answered throughout the course, and the significance of this study are also described.

The second chapter of this research will be based on the literature review. In this section of the paper, all the theories, researches, articles, and conference papers that are related to the variables being studied in this research are discussed. The literature review will be helpful for the readers to gain a better understanding of the previously conducted research researches and their findings regarding the hypothesis established in this paper.

The third chapter of this research states the research design methodology used in this paper. This chapter mentions the sample population, the demographics of the sample population, the sampling method used in this research, the measurement scales used in this research and the variables that are being analyzed in this research, the procedure through which the data will be collected, and the techniques used in the analysis of the data are all described in this chapter.

The fourth chapter is based on the analysis of the collected data.

This chapter will analyze the use of the software for the data analysis, the reliability of the gathered data, the in-depth analysis of the collected data, and based on which the hypothesis analysis is done which confirms whether the hypothesis has been accepted or rejected.

In the fifth and final chapter results of chapter four will be discussed. This chapter states whether the results are according to the initial expectation and if not, then what were the reasons behind these unexpected results. This chapter also discusses the limitations of the research, the recommendations for future studies, and finally the conclusion of the research.

Figure 1 Organization of the Thesis

## Summary

The first chapter of this research discusses the background of the research, the problem statement, the aim and objectives of this research, the research questions, and the significance of the research. The second chapter will focus on discussing the previous researches and their findings on which our hypothesis is based upon.

# CHAPTER NO 2

LITERATURE REVIEW AND HYPOTHESES DEVELOPMENT

# Literature Review

## Introduction

In this chapter, the detailed review of the variables that can cause the project to delay is done. The below-discussed variables include the client, the consultant, and the contractor, the external and internal factors. In the end, the project delays and their effects on the stakeholders are also discussed in detail.

## Definition of the variables

Successful project result of combined contributions and efforts of three major stakeholders including the Client, the consultant, and the contractor, while other significant factors that can cause the delay in the project includes the external and internal factors.

### The Contractor

The contractor in a project is an individual or an organization that is appointed by the Client or owner of the project to carry out the execution activities of the project that are required for its timely completion. In some cases where the contractor is in equipped with the expertise or resources needed in the completion of the project, then the contractor is also in charge of appointing and managing the subcontractors who have the needed knowledge and resources for the fulfilment of one or more activities critical in the completion of the project. (Hasan & Jha, 2019).

#### Contractor’s Incompetency

A research study by Gomarn, P., & Pongpeng, J. (2018) reveals that most of the delays being caused in Thailand’s oil and gas industry construction projects are because of suppliers and contractors. To avoid the risk resulting in construction projects, it is vital to identify and study the causal factors and their relationships. Thus, the keen focus of this study is to analyze those factors and assess the relationship between suppliers and contractor’s delay factors. The study was carried out in Thailand, and a 16-item based questionnaire was designed and distributed to 134 engineers, managers and supervisors of oil and gas construction projects. A test of confirmatory factor analysis (CFA) was applied with the help of Amos Version 20 software program. After the application of the CFA test, it was revealed that generally high delay caused by the suppliers and contractors was because of high regression weighs (Gomarn, & Pongpeng, 2018). Among both, the contractor caused delay involved seven major factors; site mismanagement (17%), lack of proper supervision & management (17%), improper guidelines for safety measures (16%), inability to maintain professional coordination & communication (15%), poor procurement system management (15%), meagre quality elements being used in construction (14%), delays in supplier payments (13%) as well low scheduling and planning (10%). Besides this, the delays caused by suppliers constituted chain of underdeveloped and unqualified personnel (22%), the supply of non-efficient equipment (20%), delayed deliveries of equipment’s and materials (20%), wrong quality material usage (16%), the disruptive supply of workers (16%) and incontrollable prices hike (5%) (Gomarn, & Pongpeng, 2018). Research, including the contractor’s competency, was led by Hoai et al. (2008) in which construction projects of Vietnam were focused in terms of cost overruns especially. It was a quantitative survey-based research with interviewing of about 87 Vietnamese construction project experts. The focus of the study was to determine the causal factors of prices hikes and their consequences in terms of delay. According to building and industrial projects, about 21 causes were highlighted and were ranked based on their severity, frequency as well as significance indices. (Mamata Rajgor, 2016).  Moreover, factor analysis techniques were applied to classify further these causes yielding seven factors such as lack of pressure and tardiness, incompetent workers, under-designed schedules and estimates as well as financial constraints and unskilled workforce (Le-Hoai, Dai Lee, & Lee, 2008).

HI: Contractor Related Factors Causing Project Delays in Construction Sector of Lahore Pakistan.

### The Consultant

The consultants in a project of a group of professionals who provide their expertise in a specific field. The Consultants have superior knowledge about that project than the client. The consultant provides the leadership and oversight in the execution of the project starting from the initial phase of the project to its completion. Their daily tasks include managing the resources provided by the client, managing and supervising the activities of the contractors, overseeing the project planning execution and commissioning comma and working as a liaison between the client and the contractor, to ensure the completion of project within the deadline and the budget. (Hasan & Jha, 2019).

#### Consultant’s Incompetency

Research by Owolabi et al. (2014) investigates the delay causes and their effects on projects. Lack of funds to finance the project to completion, changes in drawings, lack of effective communication among the parties involved, lack of adequate information from consultants and slow decision making are top five delay causes among 15. (Mamata Rajgor, 2016). While the top three effects of delay factors were time overrun, an increase in final project cost and waste underutilization on construction project among nine. Research use means an index for raking delay factors and their effect on the project. (Alaloul, Liew, & Zawawi, 2016).

When the completion of construction projects takes more time investment than required or agreed to results in the schedule delay. (Owolabi, Amusan, Oloke, Olusanya, Tunji-Olayeni, Dele, & Omuh, 2014). The causes of uncertainty in the project are several out which the most prevalent are improper scheduling, unrealistic demands, financial difficulties by contractor, change of environment and overtime to align with work. In residential and light construction projects delays happens mostly because of the communication gap and misunderstanding caused between contractor and client. (Alsendi, M. 2015). This issue has been studied on a global scale where the causes and their impacts are to be studied so that they can be minimized—another reason for this study to determine approaches for the successful execution of construction projects. The literature review in this respect aims to find the identification of delay reasons which are relevant to this study (Owolabi, Amusan, Oloke, Olusanya, Tunji-Olayeni, Dele, & Omuh, 2014).

Another research by Alaloul, Liew, & Zawawi (2016) suggested that the quality of a project is an essential factor to be considered.  For quality performance, coordination between project team members is required. This research was aimed at investigating the role of team coordination on projects in Malaysia. (Mamata Rajgor, 2016). A quantitative methodology was adopted in which different research papers literature was examined. The research concluded that when there is coordination among team members, it leads to a capable team and hence the success of a project can be ensured. The research also highlighted those factors through which coordination can be made possible among the team members of projects. (Alaloul, Liew, & Zawawi, 2016).

Tumi and his fellow researchers carried out a study in 2009 aimed at Zantan city of Libya to categorize the damages and delays being caused in the construction process, which were Excusable and Inexcusable delays. Among these 43 factors of uncertainty were identified and designed into a survey being subjected to a board of six comprised of clients, consultants, and workers. In total count, over eight causes were enlisted (Tumi, Omran, & Pakir, 2009).

According to Haseeb, Lu, Bibi, Dyian, & Rabbani (2011), when a project takes extra time for its completion and execution results in a process called delay. In terms of the construction industry, the schedule delay being caused is a global issue. The time overrun in a project after the due date being mentioned in the contract and the agreed timetable for the delivery of the project. There are numerous reasons due to which a schedule delay can be caused, and this study discusses those. (B. Fahathul Aziz, D. Senthil, 2015). Kumar There are several major construction companies in Pakistan. According to this research, there are about 54 factors due to which two first-class companies of all those can cause a delay. The given 54 causes have been further categorized into seven major groups including Client, Consultant, Contractor, Equipment & Labor-related, project-based, material related and externalities. For the collection of feedback from the professionals, a quantitative nature-based questionnaire survey was carried out. About 60 questionnaires were prepared out of which 42 were being sent out to significant firms (Haseeb, Lu, Bibi, Dyian, & Rabbani, 2011). The response rate was excellent, and 41 respondents were reported in this case. For the descriptive analysis of data, several measures were employed such as frequency index, severity index, weighted median tools and relative importance index.

The conclusion withdrawn from weighted median tool reveals that delays caused by clients and external factors have the highest impact of all on project schedules. (Tumi, Omran, & Pakir, 2009). A list of top 5 delays factors was enlisted with the usage of severity index which was;(1) Poor supervision and management (2) unfitting project viability study (3) Postponement of finance and payments by the holder (4) Insufficient experience of advisor and revision due to faults during construction (5) Complications in supporting the project by contractor, Unskilled workforce and effects of subsurface circumstances. (B. Fahathul Aziz, D. Senthil, 2015).  By applying the frequency index top, five delays cause identified were.

- Interruption in investment and costs by owner

- Delay in obtaining work certification

- Administration

- Measured decision making and impractical inspection and testing approaches planned in the contract

- Slow documentation by government.

Lastly, according to RII, the significant delays caused were

- Slow policy making,

- unskilled workforce

- interruption in Finance and Costs by owner,

- Delay in getting work certification from local govt authorities

- inadequate site supervision and administration (Haseeb, Lu, Bibi, Dyian, & Rabbani, 2011).

H2: Consultant Related Factors Causing Project Delays in Construction Sector of Lahore Pakistan.

### The Client

The client in a project is the main initiator of the project. The Client is the one who makes important decisions for the project, including its budget and duration—also providing and required resources for the project, including the appointment of the consultants and contractors (Hasan, & Jha, 2019).

#### Client’s Incompetency

A study being led by Fugar and Agyakwah-Baah (2010) in Ghana studied the factors behind the suspension of building construction projects to understand the prospects of significant project participants including contractors, consultants as well as clients. During this study, 32 leading causes of delay were being identified. The identified delay factors were then further categorized into other large nine groups. A questionnaire-based analysis was carried out to draw focus over major causal factors among the specified groups. The most accepted general factor identified was the one with financial group risks involved with disruption in Ghana’s construction projects (Fugar, & Agyakwah-Baah, 2010).

Research in Nigeria (2012) was conducted to determine the perception of stakeholders regarding the factors of delay and their resultant consequences. For the sample selection, a judgmental sampling technique was employed. (Megha Desai, 2013). The results obtained constituted that there were several issues found in the client’s payment approvals, last-minute changes in the design, resources shortage as well as inability to maintain and execute the task at due time. Besides this, other factors resulted in delays was mostly time management based (Akinsiku & Akinsulire, 2012).

Memon, Rahman, Abdullah, & Azis (2014) in their study on the leading causes of suspension of projects in management procurement construction projects (MARA), Malaysia found out that the main reasons behind suspension were mostly cash flow and other financial constraints as well as irresponsible behavior by contractors in managing the site as well as scheduling (Memon, Rahman, Abdullah, & Azis, 2014).

A research executed in Saudi Arabia, Assaf by Al-Khalil & Al-Hazmi, (1995) highlighted about 56 reasons for the delay being classified in 9 groups for the large conglomerate companies. The findings of this research revealed that project performance was primarily affected by due to the incompetency of the client and was stated as follows.:

- Slow illustrations approval.

- Reimbursement to contractor’s interruption due to deficiency of cash.

- Variations in Scope of work.

- Delay in Payments by the client

- Client’s delay in decision making and involvement in executive bureaucracy

H3: Client Related Factors Causing Project Delays in Construction Sector of Lahore Pakistan.

### Enterprise External Factors

The external factors in the project are the uncontrollable and mostly unpredictable factors that can influence the performance of the project. (Megha Desai, 2013). These factors include economic variables, political variables, competitors, project location, and weather conditions are all uncontrollable external factors. The external factors can both positively and negatively affect the performance of the project (Taofeeq, Adeleke, & Lee, 2020).

#### Delays Due to External Factors

A study was made on the construction industry of Europe, and analysis was done to see how the financial crisis impacts the construction industry there. Right now, the construction industry is the one most hit by the economic fall. After the manufacturing industry, the construction industry of Europe is one whose revenue contributes most to the GDP of Europe. (Towhid Pourrostam, 2012). The consolidated revenue from different states in Europe adds a higher amount to total GDP. Commercial construction markets and residential construction are both divided into western and eastern parts of Europe. West usually deals more in commercial construction; that is why more budgets are allocated to the construction industry of Western Europe. However, there is a plan to increase the budget for Eastern Europe to this year. (Nistorescu & Ploscaru, 2010).

In Egypt construction industry 43 delay causes of 7 delay groups were evaluated by Marzouk & El-Rasas, (2014) find out that Type of project bidding and award, Ineffective planning and scheduling and variation in orders/change in scope by the owner were top three delay caused by using frequency index. (Towhid Pourrostam, 2012). While by using severity index Shortage of construction materials in the market, fluctuation cost/currency and finance and payments of completed work by the owner were top three delay causes. Among seven delay groups Owner, contractor, and external related impact over project schedule delay is very high, high, and medium, respectively. Remaining four delay groups’ impact over project schedule delay was low and very low. (Marzouk & El-Rasas, 2014).

H4: External Environmental Factors (e.g. Govt rules, regulations and policies, political stability, and weather conditions) have a significant effect on project completion.

### Organizational Process Assets

The internal factors in a project include the processes and method of operations within the organizations and the processes that are interlinked between different organizations included in a project; these internal factors can have a direct and indirect impact on the performance of the tasks. (Towhid Pourrostam, 2012). These factors are controllable by the top management and can be used to increase the efficiency and the performance of the project. Some of the internal factors include the resource management procedures, reward management systems, level of autonomy of the project managers, processes for the flow of information within and between organizations. (Adeleke, Bahaudin, Kamaruddeen, Bamgbade, & Ali, 2019).

#### Delays Due to Internal Factors

A study by Eriksson (2011) determined that how rewards impact the performance of managers present for a project. The project aimed at determining whether a relationship exists between performance and rewards is given to the project teams. The project suggested that if managers are rewarded continuously and motivated extrinsically, then their execution can be improved. A detailed analysis was made to determine what type of rewards encourage managers and what should be the basis to give those rewards. This analysis was also made that either compensation will help reduce delays in construction projects. After the identification of those rewards, a vast number of articles were reviewed as a descriptive methodology to analyze if such a relation between dividends and project delay time existed in the past (Eriksson, 2011).

In another study by Assaf and AlHejji (2006) involved a time performance survey related to several types of construction projects conducted a time performance survey of different kinds of construction projects. The research was about the determination of factors causing delay also their significance regarding each of the project participant based on consultant, contractor, and owner. The area of focus in this study was the Eastern province of Saudi Arabia. The identified causes of delay during this course were total seventy-three. However, the common cause identified in this regard was “the change order”. Pourrostam and Ismail (2011) in another research focus to categorize the factors for delay in construction projects of Iran along with their consequences. This study was also questionnaire-based and was carried out to assess the viewpoint of contractors and consultants of Iran. There was a total number of 27 various causes out of which ten were listed down along with their causal effects and reasons of delay. After the keen study, it was observed that significant causes of delay were cost hikes, time mismanagement, disputes, total abandonment, litigation as well as arbitration. (Pourrostam & Ismail, 2011).

H5: Environmental Organizational Factors (e.g. company policies, procedures) have a significant effect on project completion.

### Project Manager Level of Autonomy

Project Manager level of autonomy means giving the project a complete and full-time project manager who will be responsible for all decision making and deliverables completion of the project. (Hans Georg Gemuenden, 2005).

Different research analysis shows that every project requires to give an extra level of autonomy to project managers. Nevertheless, the level of autonomy has a direct relationship with the success of a project. Autonomy varies from project to project and organization to organization. In complex projects, more autonomy is given to managers so that they are free to make every decision without concern with top management. In such projects, there is a decentralization of power and hence more governance and decision-making abilities. Autonomy level also varies according to the design and structure of the organization. Larson and Gobeli (1988) and Hobday (2000) both found that (autonomous) more decentralization of autonomy was needed in complex projects while simple or basic projects can be handled with centralization or less autonomy given to managers. Shenhar (2001) and Griffin (1997) conducted a study according to which users of the latest technology by managers also have an impact on the performance of projects. The use of the latest technology helps manger to solve the issues related to delays in the construction project by avoiding estimation errors and improved decision-making. Gemünden et al. (2005) found a correlation between the complexity level of a project and the autonomy level. More innovative projects require more autonomy to be given to managers. Project autonomy is also co-related to the level of technology used for the project as then each manager will be required to make individual decisions. (Henostroza Carrillo, 2019).  If summed up, then it means that more complex, innovative and technology-related projects, then more autonomy would be required for project managers. The higher level of autonomy and technology will help these project managers to take every possible step to reduce errors and inefficiencies that lead to delays in the construction project. Technology and autonomy in this era are only two things that can help the construction industry deal with its central problem of delays in projects. (Martinsuo & Lehtonen, 2008).

The Organizational Process Assets can be divided into two categories, the first consisting of the processes and procedures, and the second category consists of the basic knowledge of the organization. The first category consists of the policies, practices, standard operating models, and guidelines of the organization. At the same time, the second category includes the methods for storing, retrieving, and communicating the information internally and externally. All the before-mentioned OPAs should be considered in the initial project planning by the project manager (Henostroza Carrillo, 2019). The project manager, according to the level of autonomy provided to him by the organization can make temporary or permanent changes in the OPAs to meet the project goals and objectives.

From the before mention literature can be it can be concluded that the level of autonomy of project manager can have a direct impact on the OPAs of an organization which then can further cause a project delay to either prolong or reduce.  According to this theory, the level of autonomy of a project manager was used as a mediating variable for the impact of OPAs on the delay of the project. (Henostroza Carrillo, 2019).

H6: Project Manager’s level of autonomy moderates the relationship between OPAs and project delay.

### Project Location

Project location means the site allocated for construction in which the public works project ha the involvement for constructing the services like built, installed, reclaimed as mentioned in the plans or specifications. (Law Insider, 2020).

The location of the project is the construction site where the construction activities of the project are being executed according to the project plans and the relevant specifications. The area of the project can have a positive and negative impact on the completion of the project (Ramli, Malek, Hamid, Roslin, Roslan, Norhisham, & Mohd, 2018).

According to the previous studies, the delay in the construction projects depends upon the location of the project. According to research by Sambasivan and Soon (2007), the country and region in which the project is situated can have an impact on its delays. The study states that the location, government, and the type of project are significant causes of delays in the projects. The research state the factors related to the project location that affects the project delay includes but are not limited to the weather conditions, shortage of material in the local market, economic conditions of the country in which the project is located, changes in policies and regulations by the local authorities, availability of utilities and public services, and the ease and access of transportation (Sambasivan, & Soon, 2007).

According to another research regarding the project delays in the oil and gas industry states that the region that faces the most problems and delays in the oil and gas projects is the Countries in the Middle East with 87% of the project delays in comparison with Africa, Asia, Europe, Latin America and North America with the percentage delay in the of 82%, 80%, 74%, 71% and 55% respectively. The factors included in this research related to the project location consists of the regulatory changes, geopolitics issues, ease of transportation, etc. (Alaghbari, Kadir, & Salim, 2007).

The external factors of a project are the factors that are usually beyond the control of the stakeholders of the project, and these factors can have a significant impact on the successful completion of a project.  The external factors can include different variables such as the political environment, the economic environment, social environment, the location of the project, etc. (Kenley, & Seppänen, 2006). For example, the site of the project in a country where the organization has never worked will expose itself to an unknown regulatory environment, generating many risks in terms of legal feasibility, the labor framework, etc.

From the before mention literature can be it can be concluded that the project location can have a direct impact on the External factors of the project which then can further cause the project delay to either prolong or reduce.  According to this theory, the project location was used as a mediating variable for the impact of EEFs on the postponement of the project. (Kenley & Seppänen, 2006).

H7: favorable Project location moderates the relationship between EEFs and project delay.

## Hypothesized Research Model

Based on the literature above and hypothesis developed, the following model has been developed for the study.

Figure 2 Hypothesized Research Model

## Summary

The second chapter discusses some of the essential aspects of the research, answering a few general questions regarding the significant reasons of the project delays and the effect of the project delay on the stakeholders of the project. The significant factors discussed in the literature review are the client, consultant, contractors, the external factors, internal factors, and the effects of project delays. The definitions and the role of these factors in the delay of the projects were discussed in detail to increase the understanding of the readers.

# CHAPTER NO 3

RESEARCH DESIGN

# Research Design

In this chapter, methodology adopted for the study has been mentioned in detail. This chapter describes the population, sampling technique, measurement instrument and analyzing technique used in the analysis.

## Population & Sampling Technique

The target population of the study is construction firms in the city of Lahore Pakistan. The list of construction companies has been obtained from the Pakistan Engineering Council (PEC) web site. There is 466 number of companies registered with the council as per the list. The scope of these companies is different. Some of them are working in the road sector; some are working in residential building while others are concerned with commercial ones. For this study, a systematic random sampling technique has been used for selecting the companies to be surveyed for data collection. For this, each 5th company has been chosen for collecting data from consultants, clients, and contractors. From each company, project managers or people directly working on projects are given the questionnaire. Sample size has been calculated by using the below-mentioned formula:

Figure 3 Sample Size Formula

(Krejcie & Morgan, 1970)

By using the formula, the sample size comes to be 217. So, 217 companies were randomly selected from the list of PEC registered companies. Total 217 questionnaires were administered through email or google docs, from which 200 responses were collected which were completed in all respects.

Figure 4 Sampling Technique for data collection

## Measurement and Instrumentation

Different measurement scale has been used in the study. Out of all, variable one, two, three and four have been adopted from a scale developed by (Abdallah M. Odeh, 2002) for measuring the client, contractor, consultant and EEFs related delays. All these variables have been calculated by using Likert 5-point scale as Not Important, Slightly Important, Moderately Important, Very Important, Extremely Important.

While the 5th variable has been obtained from (Güngör, 2011), which is analyzed using a 5-point Likert scale staring from strongly disagree to agree strongly.

The items for variable project location have been obtained from (Hemanta Doloi a) which is analyzed by using a Likert scale starting from very low to very high.

For the last variable of the effect of delay over cost run, time overrun, litigation, and abonnements, 2 item scale has been obtained from (Wei, K.S., 2010) in which the first item was regarding the number of projects delayed. For this, the scale used was 5-point Likert scale starting from 0 to above 15. The second item is used for analyzing the percentage of projects delayed, and for this, the 5-point Likert used starts from 0% and ends at more than 30%.

Around 250 questionnaires were distributed in Lahore out of which 200 questionnaires were returned which makes 80% response rate.

| Questionnaire Distributed | Questionnaire Returned | Response Rate |
| --- | --- | --- |
| 217 | 200 | 92% |

## Variables used

•	Contractor’s Incompetency

6-items for the measurement scale will be adopted for the Contractor’s Incompetency developed by (Abdallah M. Odeh, 2002). For the measurement scale of variable, it is based upon a Likert scale of five points from Not Important to Extremely Important.

•	Consultant’s Incompetency

4-items for the measurement scale will be adopted for Consultant’s Incompetency developed by (Abdallah M. Odeh, 2002). For the measurement scale of variable, it is based upon a Likert scale of five points from Not Important to Extremely Important.

•	Client’s Incompetency

Four items are used for the measurement scale will be adopted for value creation developed by ((Abdallah M. Odeh, 2002). For the measurement scale of variable, it is based upon a Likert scale of five points from Not Important to Extremely Important.

•	EEF

Four items are used for the measurement scale will be adopted for value creation developed by (Abdallah M. Odeh, 2002). For the measurement scale of variable, it is based upon a Likert scale of five points from Not Important to Extremely Important.

•	OPA

Four items are used for the measurement scale will be adopted for value creation developed by (Güngör, 2011).  For the measurement scale of variable, it is based upon a Likert scale of five points from Strongly disagree to agree Strongly.

•	Level of Autonomy for Project Manager

Four items are used for the measurement scale will be adopted for value creation developed by. For the measurement scale of variable, it is based upon a Likert scale of five points from Strongly disagree to Strongly agree.

•	Project Location

Nine items are used for the measurement scale will be adopted for value creation developed by (Hemanta Doloi a, ⁎, Anil Sawhney b, K.C. Iyer b, Sameer Rentala). For the measurement scale of variable, it is based upon a Likert scale of five points from Strongly disagree to Strongly agree.

## Data Collection Procedure

A well-organized questionnaire incorporating the measurement scale was designed to collect the data. There were two sections in the questionnaire. Section A comprises of the demographic's questions. Section B contains the main questions regarding the variables selected for the study.

Firstly, project managers would be directly approached and updated on the study's goals, methodology and its fruitfulness. Upon receiving project managers' approval, a questionnaire was distributed in person to employees holding key positions consisting of Project Managers, Project Coordinators, Site Managers, and Site Supervisors. They were informed about the aims of the study and its possible benefits for the project-based company and asked to offer their insight into the client, contractor, consultant, and general factors that cause a delay in project completion. The researcher has answered every question that the respondents had regarding the measurement scale.

## Demographics

The first section of the questionnaire contains the demographic details concerning the classification of the participants; how long they have been in this construction business; the type of position they have worked over the years; the overall experience they had related to the project delays. This background information was essential to construct the potential credibility of the respondents and the data they provided. Due to the descriptive nature of the data being administered in this section of the research questionnaire, it was essential to use descriptive statistics (mainly % ages) to make sense from the data through useful analysis.

## Data Analysis Technique

Data is obtained through the questionnaires. Responses of the respondents are entered into the SPSS Version 21 Software’s Datasheet and PLS. First, demographics information is analyzed, which includes the job level of the respondents, years of experience, number of projects completed by them and the nature of the organization they are working in.

Secondly, a descriptive/frequency analysis has been made for each item of the variable. Each variable got computed with all items and descriptive research, which includes max value, min value, mean, sum, & standard deviation. In the third step, the correlation analysis for each variable is performed. This is done for investigating how much a variable has its impact on the other. This has been done by using SPSS. In the last step, regression analysis has been performed for investigating the collective effect of all variables. This has been done by using PLS.

Figure 5 Data Analysis Techniques

## Summary

In this chapter, there is a brief description of the methodology used for the study. It includes data analysis procedure techniques. In addition to this, the test which is applied in the study is also mentioned here.

# CHAPTER NO 4

DATA ANALYSIS

# Introduction

This chapter shows the analysis of the study. The data has been analyzed by using SPSS and PLS. Different tests have been applied to the collected data. The focus of the chapter is on the results obtained after applying the tests.

## Demographics

### Sample Composition by Organization

From the below table of organization demographics it can be seen that out of 200 responses that we received, the majority of responses that we received from the client/owner firms with accounted for about 46% with 92 replies, the second one is from the contractor firms which accounted for about 36.5% with 73 responses, in the consultant firms accounting for only 17.5% with 35 replies.

Table 1 Organizational Demographics

| Organizational Demographics |  |  |  |  |
| --- | --- | --- | --- | --- |
| Category | Frequency | % age | Valid % age | Cumulative % age |
| Client | 92 | 46.0 | 46.0 | 46.0 |
| Consultant | 35 | 17.5 | 17.5 | 63.5 |
| Contractor | 73 | 36.5 | 36.5 | 100.0 |
| Total | 200 | 100.0 | 100.0 |  |

### Position Demographics:

From 200 responses that we received for our questionnaire, the majority were from the project manager and project coordinator making up to 83 % (42% and 41% respectively) of the total responses. In contrast, the responses from the site managers and site supervisors amounted to only 14% and 4% of the total responses, respectively.

Table 2: Position Demographics

| Position Demographics |  |  |  |  |
| --- | --- | --- | --- | --- |
| Category | Frequency | % age | Valid % age | Cumulative % age |
| Project Manager | 83 | 42 | 42 | 42 |
| Project Coordinator | 82 | 41 | 41 | 83 |
| Site Manager | 28 | 14 | 14 | 97 |
| Site Supervisor | 7 | 4 | 4 | 100 |
| Total | 200 | 100 | 100 |  |

### Projects

From the data collected regarding the type of projects the sample population has been a part of, it can be observed that the majority of the respondent's health work on residential projects as it amounts to 32% of the total responses, 29% of the respondents have worked on commercial projects, 20% of the respondents have worked on the industrial projects, and the remaining 20% have the world on other projects which include projects such as shutdowns, maintenance, and production projects.

Table 3: Types of Projects Demographics

| Types of Projects |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Frequency | % age | Valid % age | Cumulative % age |
| Residential | 63 | 32 | 32 | 32 |
| Commercial | 58 | 29 | 29 | 61 |
| Industrial | 40 | 20 | 20 | 81 |
| Others | 39 | 20 | 20 | 100 |
| Total | 200 | 100 | 100 |  |

### Experience Demographics

Here the experience of the respondents comes under watch. 24 % age of the respondents had experienced less than five years. 55 % age of them were having experience of 10 years to 15 years. While 9 % age of the respondents had experience from 11 to 15 years, and only 13 % age was having experience above than 15 years.

Table 4: Experience

| Experience |  |  |  |  |
| --- | --- | --- | --- | --- |
| Category | Frequency | % age | Valid % age | Cumulative % age |
| <5 | 48 | 24 | 24 | 24 |
| 5-10 | 109 | 55 | 55 | 79 |
| 11-15 | 18 | 9 | 9 | 88 |
| >15 | 25 | 13 | 13 | 100 |
| Total | 200 | 100 | 100 |  |

### Some projects completed:

The similar trend can be observed in the table below, which represents the number of projects and everyone has done.

Table 5: No of Projects

| No of Projects |  |  |  |  |
| --- | --- | --- | --- | --- |
| Categories | Frequency | % age | Valid % age | Cumulative % age |
| 1-3 Projects | 48 | 24 | 24 | 24 |
| 4-6 Projects | 83 | 42 | 42 | 66 |
| 7-9 Projects | 38 | 19 | 19 | 85 |
| >9 | 31 | 16 | 16 | 100 |
| Total | 200 | 100 | 100 |  |

## Variables Understudy

- Dependent Variable

  - Delay In construction projects

- Independent variables

- Contractor’s Incompetency

- Consultant’s Incompetency

- Clients Incompetency

- Enterprise Environmental factors

- Organizational Process assets

- Moderators

- Project Location

- Project Manager Autonomy Level

## Reliability

To analyze the reliability of the factors involved in the delay of the project, the Cronbach’s Alpha method is used. The Cronbach’s Alpha can be used to measure the internal consistency or the reliability of the surveys and researches and is one of the most used methods to check the reliability of mostly for the questionnaires designed according to the Likert scale (Tavakol, & Dennick, 2011).

Cronbach’s Alpha coefficient of reliability usually ranges from 0 to 1. By using a formula, the Cronbach’s Alpha method calculates the reliability of the variable by considering the number of items in the scale in the mean correlation between the factors used in the measuring scale. According to George and Mallery (2003) interpretation of the Cronbach’s Alpha coefficient is shown in the table below:

Table 6 Cornbrash’s Alpha Interpretation

| CRONBACH’S ALPHA | INTERNAL CONSISTENCY |
| --- | --- |
| α ≥ 0.9 | Excellent |
| 0.9 > α ≥ 0.8 | Good |
| 0.8 > α ≥ 0.7 | Acceptable |
| 0.7 > α ≥ 0.6 | Questionable |
| 0.6 > α ≥ 0.5 | Poor |
| 0.5 > | Unacceptable |

It tells that does out questions asked are reliable for achieving our goals or not means our one goal is to see does contractor’s incompetency contribute to delays in construction projects or not. So, it will tell us that variables selected for “contractor’s Incompetency” are reliable enough to see its impact on the delays or not.

From the above table, any value of the Cornbrash’s Alpha coefficient that is above 0.7 is acceptable and is meeting the desired needs of the reliability testing and the research objective (George, & Mallery, 2003).

Table 7 Cronbach’s Alpha Analysis (Individual)

| FACTORS | CRONBACH'S ALPHA |
| --- | --- |
| COI | 0.719 |
| CNI | 0.762 |
| CLI | 0.661 |
| EEF | 0.787 |
| OPA | 0.754 |
| Effect of Delay | 0.726 |

In the above table abbreviations of the variables are used. COI stands for Contractor’s Incompetency, CLI stands for Client’s Incompetency, CNI stands for Consultant’s Incompetency, EEFs stands for Enterprise Environmental Factors, OPA stands for Organizational Process Assets.

According to the Cronbach’s Alpha analysis represented in the above table, the Coefficient for the contractor's Incompetency is 0.719 and has acceptable internal reliability, for client's Incompetency the coefficient is 0.661. Its internal reliability is questionable, consultant's Incompetency is 0.762 and has sufficient internal reliability, external factors is 0.787, and its internal reliability is satisfactory, OPA is 0.754, and its internal reliability is acceptable as well, the Level of Autonomy of Project Manager is 0.708 and has sufficient internal reliability, the project location is 0.790, and its internal reliability is acceptable. The Effects of Delay (Frequency and % average) is 0.726, and its internal reliability is also acceptable.

The states, as mentioned earlier, that each factor used in this research is reliable and significantly related to each other. The combined coefficient of all the eight elements is 0.779, which suggests that all these factors, when combined, provide acceptable internal correlation and reliability.

## Average Variance Extracted (AVE)

After analyzing the reliability through the Cronbach's Alpha method, the criteria of validity is explored through the Average Variance Extraction method, which is one of the most used variability analysis technique which indicates the average amount of variance, showing the validity of each variable.

From the below chart it can be seen that all four effects of the delays consisting of Abandonment, Litigation, Cost Overrun and Time overrun are entirely acceptable as their AVE value is 1, which is due to these being the dependent variables. While other variables including the Consultant’s Incompetency, the External Factors, and the Level of Autonomy of the Project Manager are the valid variables as their AVE value is more significant than 0.5, while the remaining variables are more or less invalid as their AVE value is lower than 0.5.

This test shows the variances in the given answers. It tells how much respondents have the same point of view in providing the solutions. The value of AVE for all variables is within the acceptable range, as shown in the following table.

Table 8 AVE

| FACTORS | AVERAGE VARIANCE EXTRACTED (AVE) |
| --- | --- |
| COI | 0.573 |
| CNI | 0.578 |
| CLI | 1.000 |
| EEF | 0.516 |
| OPA | 0.534 |
| Effect of Delay | 0.557 |

## Descriptive Analysis

This section is discussing replies of all the respondents against each item of every construct of this study as this study has used 5-point Likert Scale.

First four independent variables (Contractor’s Incompetency, Consultant’s Incompetency, Clients Incompetency and Enterprise Environmental factors) are analyzed by using the scale of “Not Very Important”, “Very Important”, “Moderately Important”, “Very Important” and “Extremely Important”.

Variables (Organization process assets, autonomy level of the project manager) were analyzed by using the scale of “strongly disagree”, “disagree, neutral”, “agree” and “strongly agree”.

Lastly, variables (Project location, Cost overrun, time overrun, litigation, and abandonment) had been analyzed by using the scale of “Very Low”, “Low”, “Average”, “High” and ‘Very High”.

### Contractor’s Incompetency

Contractor’s Incompetency is measured with the help of 5 items. The results obtained by applying the frequency distribution test over this variable are shown as follows

Table 9 Site Management issues

|  |  | Frequency | % age | Valid % age | Cumulative % age |
| --- | --- | --- | --- | --- | --- |
| Valid | Not Important | 2 | 1.0 | 1.0 | 1.0 |
|  | Slightly Important | 33 | 16.5 | 16.5 | 17.5 |
|  | Moderately Important | 72 | 36.0 | 36.0 | 53.5 |
|  | Very Important | 81 | 40.5 | 40.5 | 94.0 |
|  | Extremely Important | 12 | 6.0 | 6.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 10 Improper Construction Method

| Improper Construction Method |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 9 | 4.5 | 4.5 | 4.5 |
|  | Slightly Important | 36 | 18.0 | 18.0 | 22.5 |
|  | Moderately Important | 84 | 42.0 | 42.0 | 64.5 |
|  | Very Important | 63 | 31.5 | 31.5 | 96.0 |
|  | Extremely Important | 8 | 4.0 | 4.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 11 Improper Planning

| Improper Planning |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 7 | 3.5 | 3.5 | 3.5 |
|  | Slightly Important | 29 | 14.5 | 14.5 | 18.0 |
|  | Moderately Important | 79 | 39.5 | 39.5 | 57.5 |
|  | Very Important | 78 | 39.0 | 39.0 | 96.5 |
|  | Extremely Important | 7 | 3.5 | 3.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 12 Mistakes during the construction stage

| Mistakes during the construction stage |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 4 | 2.0 | 2.0 | 2.0 |
|  | Slightly Important | 27 | 13.5 | 13.5 | 15.5 |
|  | Moderately Important | 61 | 30.5 | 30.5 | 46.0 |
|  | Very Important | 100 | 50.0 | 50.0 | 96.0 |
|  | Extremely Important | 8 | 4.0 | 4.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 13 Inadequate contractor experience

| Inadequate contractor experience |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 9 | 4.5 | 4.5 | 4.5 |
|  | Slightly Important | 34 | 17.0 | 17.0 | 21.5 |
|  | Moderately Important | 96 | 48.0 | 48.0 | 69.5 |
|  | Very Important | 53 | 26.5 | 26.5 | 96.0 |
|  | Extremely Important | 8 | 4.0 | 4.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

For analyzing this variable, six items were analyzed in which the first statement is “Subcontractor mismanagement” only 1% is marked as not necessary. In contrast, 16% is marked as slightly important, on the other hand, 36% were marked as moderately influential, and 40 % age of the respondents was marked as essential while at the end, remaining 6 % age marked as a significant factor.

The second statement is “Site Management issues, only 4.5% is marked as not necessary, while 18% is marked as slightly important, on the other hand, 42% were marked as moderately important, and 31 % age of the respondents was marked as very important while at the end, remaining 4 % age marked as an extremely important factor.

The third statement is “Improper Construction Method, only 3.5% is marked as not important, while 14.5% is marked as slightly important, on the other hand, 39.5% were characterized as moderately important, and 39 % age of the respondents was marked as very important while at the end, remaining 3.5 % age marked as an essential factor.

The fourth statement is “Improper Planning, only 3.5% is marked as not important, while 14.5% is marked as slightly important, on the other hand, 39.5% were marked as moderately important, and 39 % age of the respondents was marked as very important while at the end, remaining 3.5 % age marked as an extremely important factor.

The fifth statement is “Mistakes during the construction stage, only 2% is marked as not important, while 13.5% is marked as slightly important, on the other hand, 30.5% were marked as moderately important, and 50 % age of the respondents was marked as very important while at the end, remaining 4 % age marked as an extremely important factor.

The sixth statement is “Inadequate contractor experience, only 4.5% is marked as not important, while 17% is marked as slightly important, on the other hand, 48% were marked as moderately important, and 26.5 % age of the respondents was marked as very important while at the end, remaining 4 % age marked as an extremely important factor.

Table 14 Contractor's Incompetency Mean

| Descriptive Statistics |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | Min | Max | Sum | Mean | Std. Deviation | Variance |
| Contractor’s Incompetency | 200 | 1.67 | 4.17 | 649.17 | 3.2458 | .54088 | .293 |
| Valid N (listwise) | 200 |  |  |  |  |  |  |

From the above table, it can be concluded that results are towards the importance of the given variable. The mean of the sample comes to be 3.2458, which is more than 3. This means that the variable encountered here is of importance to the respondents. So, it can be said that mostly, the respondents as important about the variable under consideration.

### Client’s Incompetency

Client’s Incompetency is measured with the help of 4 items. The results obtained by applying the frequency distribution test over this variable are shown as follows.

Table 15 Finances and payment of completed work

| Finances and payment of completed work |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 13 | 6.5 | 6.5 | 6.5 |
|  | Slightly Important | 26 | 13.0 | 13.0 | 19.5 |
|  | Moderately Important | 45 | 22.5 | 22.5 | 42.0 |
|  | Very Important | 94 | 47.0 | 47.0 | 89.0 |
|  | Extremely Important | 22 | 11.0 | 11.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 16 Owner interference

| Owner interference |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 11 | 5.5 | 5.5 | 5.5 |
|  | Slightly Important | 41 | 20.5 | 20.5 | 26.0 |
|  | Moderately Important | 60 | 30.0 | 30.0 | 56.0 |
|  | Very Important | 68 | 34.0 | 34.0 | 90.0 |
|  | Extremely Important | 20 | 10.0 | 10.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 17 Unrealistic contract duration and requirement imposed by the client

| Unrealistic contract duration and requirement imposed by the client |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 16 | 8.0 | 8.0 | 8.0 |
|  | Slightly Important | 28 | 14.0 | 14.0 | 22.0 |
|  | Moderately Important | 57 | 28.5 | 28.5 | 50.5 |
|  | Very Important | 88 | 44.0 | 44.0 | 94.5 |
|  | Extremely Important | 11 | 5.5 | 5.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 18 Slow decision making

| Slow decision making |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 21 | 10.5 | 10.5 | 10.5 |
|  | Slightly Important | 19 | 9.5 | 9.5 | 20.0 |
|  | Moderately Important | 75 | 37.5 | 37.5 | 57.5 |
|  | Very Important | 64 | 32.0 | 32.0 | 89.5 |
|  | Extremely Important | 21 | 10.5 | 10.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

The first statement is “Finances and payment of completed work” only 6.5% is marked as not important, 13%% are saying that this factor is slightly important, while 22% of them are having a point of view that this factor is moderately important, 47% % age is saying it is very important, and the remaining 11% are saying it is a significant factor in delaying the construction projects. For this variable, the second statement is “Owner interference” only 5.5% is marked as not important, 20.5%% are saying that this factor is slightly important, while 30% of them are having a point of view that this factor is moderately important, 34% % age are saying it is very important, and the remaining 10% are saying it is a significant factor in delaying the construction projects.  For this variable, the third statement is “Unrealistic contract duration and requirement imposed by the client” only 8% is marked as not important, 14%% are saying that this factor is slightly important, while 28% of them are having a point of view that this factor is moderately important, 44% % age are saying it is very important. The remaining 5% are saying it is an extremely important factor in delaying the construction projects.  For this variable, fourth statement is “Slow decision making ” only 10% is marked as not important, 9% are saying that this factor is slightly important, while 37% of them are having a point of view that this factor is moderately important, 32% % age are saying it is very important. The remaining 10% are saying it is extremely important factor in delaying the construction projects.

Table 19 Client's Incompetency Mean

| Descriptive Statistics |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | Minimum | Maximum | Sum | Mean | Std. Deviation | Variance |
| Client’s Incompetency | 200 | 1.00 | 5.00 | 656.50 | 3.2825 | .74698 | .558 |
| Valid N (listwise) | 200 |  |  |  |  |  |  |

From the above table, it can be concluded that results are towards the importance of the given variable. The mean of the sample comes to be 3.2825 which is more than 3. This means that the variable encountered here is of importance to the respondents. So, it can be said that mostly, the respondents as important about the variable under consideration.

### Consultant’s Incompetency

Consultant’s Incompetency is measured with the help of 4 items. The results obtained by applying the frequency distribution test over this variable are shown as follows:

Table 20 Delay in approving or preparation of shop drawings by the consultant

| Delay in approving or preparation of shop drawings by the consultant |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 32 | 16.0 | 16.0 | 16.0 |
|  | Slightly Important | 64 | 32.0 | 32.0 | 48.0 |
|  | Moderately Important | 40 | 20.0 | 20.0 | 68.0 |
|  | Very Important | 27 | 13.5 | 13.5 | 81.5 |
|  | Extremely Important | 37 | 18.5 | 18.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 21 Poor contract management

| Poor contract management |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 54 | 27.0 | 27.0 | 27.0 |
|  | Slightly Important | 49 | 24.5 | 24.5 | 51.5 |
|  | Moderately Important | 28 | 14.0 | 14.0 | 65.5 |
|  | Very Important | 30 | 15.0 | 15.0 | 80.5 |
|  | Extremely Important | 39 | 19.5 | 19.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 22 Lack of Quality assurance and control

| Lack of Quality assurance and control |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 27 | 13.5 | 13.5 | 13.5 |
|  | Slightly Important | 60 | 30.0 | 30.0 | 43.5 |
|  | Moderately Important | 40 | 20.0 | 20.0 | 63.5 |
|  | Very Important | 35 | 17.5 | 17.5 | 81.0 |
|  | Extremely Important | 38 | 19.0 | 19.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 23 Delay in approval of tests and inspection

| Delay in approval of tests and inspection |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 12 | 6.0 | 6.0 | 6.0 |
|  | Slightly Important | 62 | 31.0 | 31.0 | 37.0 |
|  | Moderately Important | 53 | 26.5 | 26.5 | 63.5 |
|  | Very Important | 42 | 21.0 | 21.0 | 84.5 |
|  | Extremely Important | 31 | 15.5 | 15.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

The first statement is “Delay in approving or preparation of shop drawings by the consultant” only 16% is marked as not important, 32%% are saying that this factor is slightly important, while 20% of them are having a point of view that this factor is moderately important, 13% % age are saying it is very important, and the remaining 18% are saying it is an extremely important factor in delaying the construction projects. For this variable, the second statement is “Poor contract management” only 27% is marked as not important, 20.5%% are saying that this factor is slightly important, while 14% of them are having a point of view that this factor is moderately important, 15% % age is saying it is very important, and the remaining 19% are saying it is an extremely important factor in delaying the construction projects.  For this variable, the third statement is “Unrealistic contract duration and requirement imposed by the client” only 8% is marked as not important, 14%% are saying that this factor is slightly important, while 28% of them are having point of view that this factor is moderately important, 44% % age are saying it is very important and the remaining 5% are saying it is extremely important factor in delaying the construction projects.  For this variable, fourth statement is “Slow decision making ” only 10% is marked as not important, 9% are saying that this factor is slightly important, while 37% of them are having point of view that this factor is moderately important, 32% % age are saying it is very important and the remaining 10% are saying it is extremely important factor in delaying the construction projects.

So, after seeing this whole table and results of the whole of items under this construct we can say that from respondent’s point of view, this variable does have large impact in delaying the construction projects. Most of them had responded very important and moderately important.

Table 24 Consultant's Incompetency Mean

| Descriptive Statistics |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | Minimum | Maximum | Sum | Mean | Std. Deviation | Variance |
| Consultant’s Incompetency | 200 | 1.00 | 5.00 | 656.50 | 3.2825 | .74698 | .558 |
| Valid N (listwise) | 200 |  |  |  |  |  |  |

From the above table, it can be concluded that results are towards the importance of the given variable. The mean of the sample comes to be 3.2825 which is more than 3. This mean that the variable encountered here is of importance to the respondents. So, it can be said that mostly, the respondents as important about the variable under consideration.

### EEFs

EEFs is measured with help of 4 items. The results obtained by applying the frequency distribution test over this variable are shown as follows:

Table 25 Weather conditions

| Weather conditions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 20 | 10.0 | 10.0 | 10.0 |
|  | Slightly Important | 44 | 22.0 | 22.0 | 32.0 |
|  | Moderately Important | 108 | 54.0 | 54.0 | 86.0 |
|  | Very Important | 17 | 8.5 | 8.5 | 94.5 |
|  | Extremely Important | 11 | 5.5 | 5.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 26 Regulatory Changes

| Regulatory Changes |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 11 | 5.5 | 5.5 | 5.5 |
|  | Slightly Important | 61 | 30.5 | 30.5 | 36.0 |
|  | Moderately Important | 105 | 52.5 | 52.5 | 88.5 |
|  | Very Important | 7 | 3.5 | 3.5 | 92.0 |
|  | Extremely Important | 16 | 8.0 | 8.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 27 Problem With neighbors

| Problem With neighbours |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 21 | 10.5 | 10.5 | 10.5 |
|  | Slightly Important | 47 | 23.5 | 23.5 | 34.0 |
|  | Moderately Important | 106 | 53.0 | 53.0 | 87.0 |
|  | Very Important | 5 | 2.5 | 2.5 | 89.5 |
|  | Extremely Important | 21 | 10.5 | 10.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 28 Unforeseen ground conditions

| Unforeseen ground conditions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Not Important | 21 | 10.5 | 10.5 | 10.5 |
|  | Slightly Important | 50 | 25.0 | 25.0 | 35.5 |
|  | Moderately Important | 102 | 51.0 | 51.0 | 86.5 |
|  | Very Important | 15 | 7.5 | 7.5 | 94.0 |
|  | Extremely Important | 12 | 6.0 | 6.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

First statement is “Weather conditions” only 10% is marked as not important, 22%% are saying that this factor is slightly important, while 54% of them are having point of view that this factor is moderately important, 8% % age are saying it is very important and the remaining 5% are saying it is extremely important factor in delaying the construction projects.

For this variable, second statement is “Regulatory Changes” only 5% is marked as not important, 30%% are saying that this factor is slightly important, while 52% of them are having point of view that this factor is moderately important, 3% % age are saying it is very important and the remaining 8% are saying it is extremely important factor in delaying the construction projects.

For this variable, third statement is “Problem With neighbors” only 10% is marked as not important, 23% are saying that this factor is slightly important, while 53% of them are having point of view that this factor is moderately important, 2% % age are saying it is very important and the remaining 10% are saying it is extremely important factor in delaying the construction projects.

For this variable, fourth statement is “Unforeseen ground conditions” only 10% is marked as not important, 25% are saying that this factor is slightly important, while 51% of them are having point of view that this factor is moderately important, 7% % age are saying it is very important and the remaining 6% are saying it is extremely important factor in delaying the construction projects.

So, after seeing this whole table and results of the whole of items under this construct we can say that from respondent’s point of view, this variable does have large impact in delaying the construction projects. Most of them had responded very important and moderately important.

Table 29 EEFs Mean

| Descriptive Statistics |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | Minimum | Maximum | Sum | Mean | S. D | Variance |  |
| EEFs | 200 | 1.00 | 5.00 | 554.00 | 2.7700 | .68882 |  | .474 |
| Valid N (listwise) | 200 |  |  |  |  |  |  |  |

From the above table, it can be concluded that results are towards the importance of the given variable. The mean of the sample comes to be 2.7700 which is less than 3. This mean that the variable encountered here is of no importance to the respondents. So, it can be said that mostly, the respondents as not important about the variable under consideration.

### OPAs

OPA is measured with help of 4 items. The results obtained by applying the frequency distribution test over this variable are shown as follows:

Table 30 Financial rewards (salary, bonus, and perquisite)

| Financial rewards (salary, bonus, and perquisite) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 61 | 30.5 | 30.5 | 30.5 |
|  | Disagree | 22 | 11.0 | 11.0 | 41.5 |
|  | Uncertain | 27 | 13.5 | 13.5 | 55.0 |
|  | Agree | 49 | 24.5 | 24.5 | 79.5 |
|  | Strongly Agree | 41 | 20.5 | 20.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 31 Price increases of salary raises performance of the employee

| Price increases of salary raises performance of the employee |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 12 | 6.0 | 6.0 | 6.0 |
|  | Disagree | 43 | 21.5 | 21.5 | 27.5 |
|  | Uncertain | 45 | 22.5 | 22.5 | 50.0 |
|  | Agree | 62 | 31.0 | 31.0 | 81.0 |
|  | Strongly Agree | 38 | 19.0 | 19.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 32 Benefits such as rent, clothing or fuel

| Benefits such as rent, clothing or fuel |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 17 | 8.5 | 8.5 | 8.5 |
|  | Disagree | 45 | 22.5 | 22.5 | 31.0 |
|  | Uncertain | 47 | 23.5 | 23.5 | 54.5 |
|  | Agree | 50 | 25.0 | 25.0 | 79.5 |
|  | Strongly Agree | 41 | 20.5 | 20.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 33 Bonuses given on special days

| Bonuses given on special days |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 30 | 15.0 | 15.0 | 15.0 |
|  | Disagree | 49 | 24.5 | 24.5 | 39.5 |
|  | Uncertain | 46 | 23.0 | 23.0 | 62.5 |
|  | Agree | 48 | 24.0 | 24.0 | 86.5 |
|  | Strongly Agree | 27 | 13.5 | 13.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

First statement is “Financial rewards (salary, bonus, and perquisite)” only 30% is marked as strongly disagree, 11% are saying that they disagree with this statement, while 13% of them are having point of view that they are not sure of this one, on the other hand, 24% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 20% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

In this variable, the second factor “Price increases of salary raises performance of the employee)” only 6% is marked as strongly disagree, 21% are saying that they disagree with this statement, while 32% of them are having point of view that they are not sure of this one, on the other hand, 21% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 19% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

In this variable, the 3rd factor “Benefits such as rent, clothing or fuel” only 8% is marked as strongly disagree, 22% are saying that they disagree with this statement, while 23% of them are having point of view that they are not sure of this one, on the other hand, 25% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 20% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

In this variable, the 4th factor “Bonuses given on special days” only 15% is marked as strongly disagree, 24% are saying that they disagree with this statement, while 23% of them are having point of view that they are not sure of this one, on the other hand, 24% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 13% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

So, after seeing this whole table and results of the whole of items under this construct we can say that from respondent’s point of view, this variable does have large impact in delaying the construction projects. Most of them had responded strongly agree and agree.

Table 34 OPA Mean

| Descriptive Statistics |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | Minimum | Maximum | Sum | Mean | Std. Deviation | Variance |
| OPAs | 200 | 1.25 | 5.00 | 626.00 | 3.1300 | .81904 | .671 |
| Valid N (listwise) | 200 |  |  |  |  |  |  |

From the above table, it can be concluded that results are towards the importance of the given variable. The mean of the sample comes to be 3.1300 which is more than 3. This mean that the variable encountered here is of importance to the respondents. So, it can be said that mostly, the respondents as important about the variable under consideration.

### Project Manager Autonomy

Project Manager level of Autonomy is measured with help of 4 items. The results obtained by applying the frequency distribution test over this variable are shown as follows:

Table 35 The project Manager could freely choose tolls and technologies

| The project Manager could freely choose tolls and technologies |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 11 | 5.5 | 5.5 | 5.5 |
|  | Disagree | 27 | 13.5 | 13.5 | 19.0 |
|  | Uncertain | 120 | 60.0 | 60.0 | 79.0 |
|  | Agree | 26 | 13.0 | 13.0 | 92.0 |
|  | Strongly Agree | 16 | 8.0 | 8.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 36 The project Manager had control over what he was supposed to accomplish

| The project Manager had control over what he was supposed to accomplish |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 16 | 8.0 | 8.0 | 8.0 |
|  | Disagree | 28 | 14.0 | 14.0 | 22.0 |
|  | Uncertain | 112 | 56.0 | 56.0 | 78.0 |
|  | Agree | 33 | 16.5 | 16.5 | 94.5 |
|  | Strongly Agree | 11 | 5.5 | 5.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 37 The project Manager was granted autonomy on how to handle all requirements and changes

| The project Manager was granted autonomy on how to handle all requirements and changes |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 21 | 10.5 | 10.5 | 10.5 |
|  | Disagree | 19 | 9.5 | 9.5 | 20.0 |
|  | Uncertain | 119 | 59.5 | 59.5 | 79.5 |
|  | Agree | 20 | 10.0 | 10.0 | 89.5 |
|  | Strongly Agree | 21 | 10.5 | 10.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 38 The project Manager was free to assign personnel to the Project

| The project Manager was free to assign personnel to the Project |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 12 | 6.0 | 6.0 | 6.0 |
|  | Disagree | 39 | 19.5 | 19.5 | 25.5 |
|  | Uncertain | 95 | 47.5 | 47.5 | 73.0 |
|  | Agree | 33 | 16.5 | 16.5 | 89.5 |
|  | Strongly Agree | 21 | 10.5 | 10.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

First statement is “The project Manager was allowed to freely choose tolls and technologies” only 5% is marked as strongly disagree, 13% are saying that they disagree with this statement, while 60% of them are having point of view that they are not sure of this one, on the other hand, 13% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 8% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

In this variable, the 2nd factor “The project Manager had control over what he was supposed to accomplish” only 8% is marked as strongly disagree, 14% are saying that they disagree with this statement, while 56% of them are having point of view that they are not sure of this one, on the other hand, 16% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 5% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

In this variable, the 3rd factor “The project Manager was granted autonomy on how to handle all requirements and changes” only 10% is marked as strongly disagree, 9% are saying that they disagree with this statement, while 59% of them are having point of view that they are not sure of this one, on the other hand, 10% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 10% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

In this variable, the 4th factor “The project Manager was free to assign personnel to the Project” only 6% is marked as strongly disagree, 19% are saying that they disagree with this statement, while 47% of them are having point of view that they are not sure of this one, on the other hand, 16% % age are saying that they do agree with the statement in delaying the construction projects and lastly the remining 10% are saying that they strongly agree with this statement that this factor contributes in delaying the construction projects.

So, after seeing this whole table and results of the whole of items under this construct we can say that from respondent’s point of view, this variable does have large impact in delaying the construction projects. Most of them had responded uncertain about this which shows that people do not think that autonomy level of project manager can have negative impact on the delays of construction projects.

Table 39 project Manager Level of Autonomy

| Descriptive Statistics |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | Minimum | Maximum | Sum | Mean | Std. Deviation | Variance |
| Project Manager Level of Autonomy | 200 | 1.00 | 5.00 | 604.25 | 3.0212 | .70210 | .493 |
| Valid N (listwise) | 200 |  |  |  |  |  |  |

From the above table, it can be concluded that results are towards the importance of the given variable. The mean of the sample comes to be 3.0212 which is more than 3. This mean that the variable encountered here is of importance to the respondents. So, it can be said that mostly, the respondents as important about the variable under consideration.

### Project Location

Project Location is measured with help of 9 items. The results obtained by applying the frequency distribution test over this variable are shown as follows:

Table 40 Restricted access at site

| Restricted access at site |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 48 | 24.0 | 24.0 | 24.0 |
|  | Disagree | 50 | 25.0 | 25.0 | 49.0 |
|  | Uncertain | 40 | 20.0 | 20.0 | 69.0 |
|  | Agree | 14 | 7.0 | 7.0 | 76.0 |
|  | Strongly Agree | 48 | 24.0 | 24.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 41 Extreme weather conditions

| Extreme weather conditions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 37 | 18.5 | 18.5 | 18.5 |
|  | Disagree | 49 | 24.5 | 24.5 | 43.0 |
|  | Uncertain | 61 | 30.5 | 30.5 | 73.5 |
|  | Agree | 10 | 5.0 | 5.0 | 78.5 |
|  | Strongly Agree | 43 | 21.5 | 21.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 42 Slow decisions from owner

| Slow decisions from owner |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 54 | 27.0 | 27.0 | 27.0 |
|  | Disagree | 43 | 21.5 | 21.5 | 48.5 |
|  | Uncertain | 38 | 19.0 | 19.0 | 67.5 |
|  | Agree | 43 | 21.5 | 21.5 | 89.0 |
|  | Strongly Agree | 22 | 11.0 | 11.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 43 Delay in material delivery by vendors

| Delay in material delivery by vendors |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 94 | 47.0 | 47.0 | 47.0 |
|  | Disagree | 56 | 28.0 | 28.0 | 75.0 |
|  | Uncertain | 36 | 18.0 | 18.0 | 93.0 |
|  | Agree | 11 | 5.5 | 5.5 | 98.5 |
|  | Strongly Agree | 3 | 1.5 | 1.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 44 Site accidents due to negligence

| Site accidents due to negligence |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 86 | 43.0 | 43.0 | 43.0 |
|  | Disagree | 47 | 23.5 | 23.5 | 66.5 |
|  | Uncertain | 33 | 16.5 | 16.5 | 83.0 |
|  | Agree | 15 | 7.5 | 7.5 | 90.5 |
|  | Strongly Agree | 19 | 9.5 | 9.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 45 Site accidents due to lack of safety measures

| Site accidents due to lack of safety measures |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 84 | 42.0 | 42.0 | 42.0 |
|  | Disagree | 33 | 16.5 | 16.5 | 58.5 |
|  | Uncertain | 35 | 17.5 | 17.5 | 76.0 |
|  | Agree | 20 | 10.0 | 10.0 | 86.0 |
|  | Strongly Agree | 28 | 14.0 | 14.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 46 Unforeseen ground conditions

| Unforeseen ground conditions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 61 | 30.5 | 30.5 | 30.5 |
|  | Disagree | 61 | 30.5 | 30.5 | 61.0 |
|  | Uncertain | 59 | 29.5 | 29.5 | 90.5 |
|  | Agree | 11 | 5.5 | 5.5 | 96.0 |
|  | Strongly Agree | 8 | 4.0 | 4.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 47 Hostile political conditions

| Hostile political conditions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 60 | 30.0 | 30.0 | 30.0 |
|  | Disagree | 61 | 30.5 | 30.5 | 60.5 |
|  | Uncertain | 40 | 20.0 | 20.0 | 80.5 |
|  | Agree | 14 | 7.0 | 7.0 | 87.5 |
|  | Strongly Agree | 25 | 12.5 | 12.5 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

Table 48 Inaccurate specification of site condition

| Inaccurate specification of site condition |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Frequency | % age | Valid % age | Cumulative % age |
| Valid | Strongly Disagree | 53 | 26.5 | 26.5 | 26.5 |
|  | Disagree | 83 | 41.5 | 41.5 | 68.0 |
|  | Uncertain | 33 | 16.5 | 16.5 | 84.5 |
|  | Agree | 17 | 8.5 | 8.5 | 93.0 |
|  | Strongly Agree | 14 | 7.0 | 7.0 | 100.0 |
|  | Total | 200 | 100.0 | 100.0 |  |

This factor has been analyzed to see its negative effect on the project delays. It was the moderator in the model. From the responses, most of the people were in point of view that favorable conditions of project location cannot have a negative effect on the delays of the project as more than 50 % age of the respondents gave the answer as “strongly disagree or “disagree”.

Table 49 Project Location Mean

| Descriptive Statistics |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | N | Minimum | Maximum | Sum | Mean | Std. Deviation | Variance |
| Location | 200 | 1.00 | 4.11 | 482.00 | 2.4100 | .78578 | .617 |
| Valid N (listwise) | 200 |  |  |  |  |  |  |

From the above table, it can be concluded that results are towards the importance of the given variable. The mean of the sample comes to be 2.4100, which is less than 3. This means that the variable encountered here is of no importance to the respondents. So, it can be said that mostly, the respondents as not important about the variable under consideration.

## Path Coefficients

This analysis has been done by PLS, which is used for analyzing the relationship, effect, and magnitude of the impact of one variable to the other.

Table 50 Significance Testing Results of the Structural Model Path Coefficients

| Hypothesis | Path | Path Coefficients | t values | p Values | Hypothesis |
| --- | --- | --- | --- | --- | --- |
| H1 | COI -> Effect of Delay | 0.182 | 2.820 | 0.005 | Accepted |
| H2 | CNI -> Effect of Delay | 0.303 | 6.192 | 0.000 | Accepted |
| H3 | CLI -> Effect of Delay | 0.187 | 2.017 | 0.044 | Accepted |
| H4 | EEFs -> Effect of Delay | -0.186 | 1.748 | 0.080 | Rejected |
| H5 | OPA -> Effect of Delay | 0.164 | 2.695 | 0.007 | Accepted |
| H6 | PMA*OPA -> Effect of Delay | -0.243 | 2.533 | 0.011 | Accepted |
| H7 | PL*EF -> Effect of Delay | 0.062 | 1.054 | 0.292 | Rejected |

- Path coefficient shows the direct or indirect relationship among the variables. Its value should be > 0.1

- t values show the compatibility or incompatibility of our collected data with the hypothesis. It should be > 1.96

- p-value shows how much the probability is there to accept the hypothesis. It should be < 0.05. We have adopted a single tail method, which is why we are using 0.05.

Hypothesis 1 to 3

Path coefficient gives us an indication about the direct or indirect relationships among the variables.  From the table, it is observed that in hypothesis 1 to 3, IVs have a direct positive relationship with DV, which means that incompetency in contractor, consultant and clients can delay the project. Also, the p-values are less than 0.05, which means that these hypotheses are accepted and valid.

In the tables, as mentioned earlier, the first hypothesis shows that there is a positive impact of contractor’s incompetency in delaying the construction projects. The result of the second hypothesis tells that there is a significant positive impact of a consultant’s incompetency in delaying the construction projects. The reason for this significant relationship might be the role of consultants in the society of Pakistan, where most consultants undergo an in-depth analysis of projects at a time. The results of the third hypothesis show that there is again a positive impact of client’s incompetency in delaying the construction projects, the reason for this significant relationship might be the payments are paid by the clients. If payments are not paid timely, it affects the project progress tremendously. Secondly, the reason might be the attitude of respondents towards filling the questionnaire.

Hypothesis 4

Whereas, in hypothesis, No.4 independent variable (EEF) has a negative relationship with the delay of the project. This shows that EEF does not contribute to delaying the project directly. The value here is more than 0.05, which is the basis of rejecting the hypothesis no. 4.

Hypothesis 5

In hypothesis no.5, the value of the path coefficient is 0.164, which means that OPAs does have a direct positive relationship with the delay in construction projects. It shows that 1 per cent change in IV (OPA) is having its effect of 16.4 per cent in the DV (delays). The value of t is 2.695, which is also under the acceptable range. The value of p here is 0.0.7 making this hypothesis accepted. This fifth hypothesis shows that there is a positive impact of OPAs in delaying the projects. The reason behind this might be that over documentation may consume more time than expected, causing delays.

Hypothesis 6

In the same manner, the sixth hypothesis which states that “Good level of project manager autonomy can negatively impact the delay of construction projects by handling OPAs” also accepted as the value of p is less than 0.05 making it acceptable. Which means that if project managers are given the great autonomy and authority, they can handle the process of the organization timely causing fewer delays in the construction projects. The value of the path coefficient is -0.243, which means it is negatively moderating the delays. It does not have a direct positive effect in minimizing the delays in a construction project.

Hypothesis 7

Hypothesis 7 states that “There is a negative effect of good and favorable project location in causing a delay of construction projects by handling EEFs”. In this, the path coefficient is 0.062, which shows it does have positive direct relation, but its significance is very low (p>0.05), becoming the basis of rejecting the hypothesis. Also, the value of t in this one is less than 1.96, and it is rejected as dealing the EEFs by appropriate project location also does not help in minimizing the delays.

CHAPTER NO 5

DISCUSSION & CONCLUSION

# Conclusion, Discussion, Limitations and Future Research Suggestion

## Discussion

This study is about analyzing the causes and impact of construction projects in Lahore Pakistan. For this purpose, independent variables such as contractor’s incompetency, consultant’s incompetency, client’s competency, enterprise environmental factors, and organizational process assets have been selected. Also, two moderators (Project Manager’s level of autonomy & Location of Project) have been used to foresee the effect of these in minimizing the delays in construction projects. Additionally, the effect of project delay on cost overrun, time overrun, Litigation and abonnements of concerned companies have also been analyzed in the study. For analysis, a questionnaire containing two sections was distributed among 250 respondents, which gave 200 responses to the author. From the first section, the demographics questions such as level of experience, organization of the respondent, their position in the organization and number of projects completed by them.

In the analysis, first descriptive analysis has been performed, which shows most of the respondents were geeing with statements of causing a delay in the construction projects. For analysis purpose, the descriptive analysis had been performed first, in which six items had been used for the first variable, namely contactor’s incompetency. The first item was Subcontractor mismanagement for which, only 6% is marked as not important, 38.5% kept it as moderately necessary, and 3% of responses were in important fields. The second item is “Site Management issues” for which only 1% of responses were not important, 36% were on average and 6% marked as important. The third statement was “Improper Construction Method” 4% of this statement responses were marked as not important and then 42% of the statement were responded it as moderately important, and 4% of this statement is marked as extremely Important. The fourth statement was “Improper Planning” 3% of respondents said about this statement that it is not important 39% marked it average, and 3% respondents said it is very important. The fifth statement was “Mistakes during construction stage” 2% of responses were of not important about this statement, and 30% responses were of average about it, and 4% marked it as Important. The sixth statement was “Inadequate contractor experience” 4% responses were of not important 48% were in the middle and says it is of average 4% respondents were at important side of this statement.

For the second variable of the client’s incompetency, four items were analyzed in which the first one was

“Finances and payment of completed work” 47% age were saying it is very important and the remaining 11% were saying it is extremely important factor in delaying the construction projects. For this variable, the second statement was “Owner interference” 34% age was saying it is imperative, and the remaining 10% were saying it is a significant factor in delaying the construction projects.  For this variable, the third statement was “Unrealistic contract duration and requirement imposed by the client” 44% age were saying it is essential and the remaining 5% were saying it is an extremely important factor in delaying the construction projects.  The fourth statement was “Slow decision making” 32% were saying it is very important, and the remaining 10% were saying it is a significant factor in delaying the construction projects.

The third variable analyzed in the study was the consultant’s variable, for which four items were used. The first statement was “Delay in approving or preparation of shop drawings by the consultant” 13% were saying it is imperative and the remaining 18% were saying it is an extremely important factor in delaying the construction projects. For this variable, the second statement was “Poor contract management” 15% was saying it is very important, and the remaining 19% were saying it is an extremely important factor in delaying the construction projects. The third statement was “Unrealistic contract duration and requirement imposed by the client” 44% was saying it is very important and the remaining 5% were saying it is an extremely important factor in delaying the construction projects.  The fourth statement was “Slow decision making” 32% were saying it is very important, and the remaining 10% were saying it is an extremely important factor in delaying the construction projects.

The fourth variable used was enterprise environmental factors for which four items were used. The first statement was “Weather conditions” for which 8% said it is very important and the remaining 5% are saying it is an extremely important factor in delaying the construction projects. The second statement was “Regulatory Changes” 3% were saying it is very important, and the remaining 8% are saying it is an extremely important factor in delaying the construction projects. The third statement was “Problem With neighbors” 2% are saying it is very important, and the remaining 10% are saying it is an extremely important factor in delaying the construction projects.  The fourth statement was “Unforeseen ground conditions” 7% were saying it is very important, and the remaining 6% were saying it is an extremely important factor in delaying the construction projects.

The fifth variable used in the analysis was OPAs, for which four items were used. The first statement was “Financial rewards (salary, bonus, and perquisite)” 24% were saying that they do agree with the statement in delaying the construction projects and lastly the remaining 20% were saying that they strongly agree with this statement. Second factor “Price increases of salary raise the performance of the employee)” 21% were saying that they do agree with the statement in delaying the construction projects and lastly the remaining 19% were saying that they strongly agree with this statement that this factor contributes in delaying the construction projects. 3rd-factor “Benefits such as rent, clothing or fuel” 25% were saying that they do agree with the statement in waiting the construction projects and lastly the remaining 20% were saying that they strongly agree with this statement. 4th-factor “Bonuses given on special days” 24% were saying that they do agree with the information in delaying the construction projects and lastly the remaining 13% were saying that they strongly agree with this statement.

The sixth variable used in the study was “Project manager level of autonomy” for which four items were used.  The first statement was “The Project Manager was allowed to choose tolls and technologies freely” 13% were saying that they do agree with the statement in delaying the construction projects and lastly the remaining 8% said that they strongly agree with this statement. 2nd factor “The project Manager had control over what he was supposed to accomplish,” 16% said that they do agree with the statement in delaying the construction projects and lastly the remaining 5% said that they strongly agree with this statement. 3rd factor “The project Manager was granted autonomy on how to handle all requirements and changes,” 10% said that they do agree with the statement in delaying the construction projects and lastly the remaining 10% said that they strongly agree with this statement. 4th factor “The project Manager was free to assign personnel to the Project,” 16% said that they do agree with the statement in delaying the construction projects and lastly the remaining 10% are saying that they strongly agree with this statement.

The project location was the seventh variable in this study, for which nine items were used. This factor has been analyzed to see its negative effect on project delays. It was the moderator in the model. From the responses, most of the people were in point of view that favorable conditions of project location cannot have an adverse effect on the delays of the project as more than 50 % age of the respondents gave the answer as “strongly disagree or “disagree.

This study is done to conclude about the causes and impact of project delays in construction Sector in Lahore Pakistan. The causes are measured through contractor’s incompetency, consultant’s incompetency, client’s incompetency, EEFs, & OPAs, and it is concluded that contractor’s incompetency, consultant’s incompetency, client’s incompetency & OPAs have a positive impact on project delay but not EEFs.

Further, the path coefficient analysis was applied on the research variables in order to check the validity of the initial hypothesis coming up with the same conclusion as the correlation analysis stating that all the variables except the external factors and the project location plays a significant role in the delays of projects. While the regression analysis and the path coefficient analysis also analyze the relationship between the effects of project delays with its variables consisting of the cost overrun, time overrun, Litigation and abandonment. The findings of these analysis state that if the project by any means gets delayed, the most probability is of legal issues to arise. In contrast, the abandonment of the project although having significant chances of happening but is the least probable about other variables. We have seen from the results of regression only two hypotheses have nominal value at a 5% significance level, and the remaining nine have significant values at 5% significance level. The remaining variables contractor’s incompetency, consultant’s incompetency, client’s incompetency, and organizational process assets make a significant impact on Project delay. Also, the moderator project location on EEFs does not have a significant impact, and it does not help in minimizing the project delay. On the other hand, another moderator namely “project manager level of autonomy” in dealing with OPAs does have a negative impact in project delay which means that if PMs are given the authority and autonomy, they can help in minimizing the delays of projects in the construction industry.

## Conclusion

The objective of this research was to investigate the causes of delays in construction projects and the effect of the project delay on its stakeholders. The impact of factors involved in the delay of the project that is related to the contractor, client, consultant, internal and external factors was analyzed in this research. The data for this research was collected through a structured questionnaire consisting of 50 questions was distributed among the population of 250 individuals consisting of project managers, project coordinators, site managers, and site supervisors. To analyze the data, various statistical analysis technique was used including but not limited to reliability analysis, factor analysis, path coefficient analysis, computation of means and standard deviations, regression analysis and correlation analysis.

The objective of this research was to investigate the causes of delays in construction projects and the effect of the project delay on its stakeholders, which was achieved successfully. The findings of the research state that the factors related to the consultant-client contractor and the internal factors have a significant impact on the delay in the construction projects, while the external factors and the project location have a minimal effect on the project delay. This research further provides the shares with the limitations of this research paper and the recommendations for the construction firms.

The factor that had the most significant impact on the delay of the construction projects was the incompetency of the consultant. From this factor, the variable with the most impact was the delay in the approvals of tests and inspection by the consultant. So to reduce the probability of the project delay, the project managers should prepare a strategy and a policy to ensure that the unnecessary delays in the approval of the tests and inspection are reduced, while at the same time ensuring that the quality assurance and control of the project by the consultants are efficient as this is another reason for the project to get delayed.

## Limitations

Small sample size has been used in the study, but this thing should not nullify the conclusions drawn. Also, there is limited time and resources available for the completion of the course. One country, one city, and only 20 private firms are not enough and do not helps in representing the big picture of project delays. In addition to this, there is a specific concentration on the quantitative method for the analysis. Still, it has been suggested that both quantitative and qualitative needs be used for generalizability of the results. The study under consideration is not representing the whole industry of construction.

## Future Recommendations

As noted throughout the research, project manager’s autonomy helps minimize the project delays. Which shows that if project managers are given the authority, they can handle the projects more appropriately and delays can be minimized. So, it is recommended to do the needful. The findings can, therefore, be used as a guidance that PMs can review and handle their projects and if can make decisions by their own, it can provide more value; gaining recognition and completion of projects within pre-defined time and budget.

# References

Abdalla M. Odeh (2002), Causes of construction delays: traditional contracts, international journal of project management, 67-73.

Adeleke, A. Q., Bahaudin, A. Y., Kamaruddeen, A. M., Bamgbade, J. A., & Ali, M. W. (2019). An empirical analysis of organizational external factors on construction risk management. Int J Suppl Chain Manag, 8(1), 932.

Aibinu, A. A., & Jagboro, G. O. (2002). The effects of construction delays on project delivery in Nigerian construction industry. International journal of project management, 20(8), 593-599.

Alaghbari, W. E., Kadir, M. R. A., & Salim, A. (2007). The significant factors causing delay of building construction projects in Malaysia. Engineering, Construction and Architectural Management.

Alaloul, W. S., Liew, M. S., & Zawawi, N. A. W. A. (2016). Identification of coordination factors affecting building projects performance. Alexandria Engineering Journal, 55(3), 2689-2698.

Ali, M., Iqbal, S., & Iqbal, Q. (2020). Causes of Delay in the Establishment of Public Sector University in Newly Merged Districts of KP, Pakistan. International Journal of Engineering Works, 7(05), 221-227.

Alsendi, M. (2015). Studying the effect of decision making on delayed construction projects.  (Master of Engineering), Dissertation, The George Washington University, Manama, Kingdom of Bahrain

Assaf, S., Hassanain, M. A., & Mughal, H. (2014). Effectiveness of project teams and their impact on the performance of Saudi construction projects. Research Journal of Applied Sciences, Engineering and Technology, 7(24), 5148-5156.

Aziz, B. F., & Kumar, D. S (2015). Impacts of Uncertainty Factors in Construction Projects.

B. Fahathul Aziz, D. Senthil Kumar “Impacts of Uncertainty Factors in Construction Projects” (Volume 4, Issue 1, March 2015).

Babbie, E. R. (1990). Survey research methods (Vol. 2). Belmont, CA: Wadsworth Publishing Company.

DA Dillman, P. S. (1994). How to conduct your own survey.

Desai, M., & Bhatt, R. (2013). Critical causes of delay in residential construction projects: case study of central Gujarat region of India. International Journal of Engineering Trends and Technology, 4(4), 762-768.

Eriksson, T. (2011). Reward Systems and Incentives in a Project Based Organisation Identification of Reward Systems and Incentives influencing Construction Site Managers.

Fugar, F. D., & Agyakwah-Baah, A. B. (2010). Delays in building construction projects in Ghana. Australasian Journal of Construction Economics and Building, The, 10(1/2), 128.

Gomarn, P., & Pongpeng, J. (2018). Causes of construction delay from contractors and suppliers in Thailand's oil and gas platform projects. In MATEC Web of Conferences (Vol. 192, p. 02008). EDP Sciences.

Gwanhoo Lee and Weidong Xia (2010), Toward Agile: An Integrated Analysis of Quantitative and Qualitative Field Data on Software Development Agility, Management Information Systems Research Center, University of Minnesota.

Hans Georg Gemuenden (2005), The Influence of Project Autonomy on Project Success, International Journal of Project Management 23(5):366-373 · July 2005.

Hasan, A., & Jha, K. N. (2019). Client and contractor roles in schedule incentive/disincentive projects. Engineering, Construction and Architectural Management.

Henostroza Carrillo, P. S. (2019). Aplicación de los lineamientos de la gestión de la calidad del pmbok-v6 enla implementación del sistema iso 9001: 2015 en una empresa constructora para la generación de valor agregado-Ancash-2018.

Haseeb, M., Bibi, A., & Rabbani, W. (2011). Problems of projects and effects of delays in the construction industry of Pakistan. Australian journal of business and management research, 1(5), 41-50.

Haseeb, M., Lu, X., Bibi, A., Dyian, M. U., & Rabbani, W. (2011). Causes and effects of delays in large construction projects of Pakistan. Kuwait Chapter of Arabian Journal of Business and Management Review, 33(832), 1-25.

Hemanta Doloi a, ⁎, Anil Sawhney b, K.C. Iyer b, Sameer Rentala (2012), Analyzing factors affecting delays in Indian construction projects, International journal of project management, http://dx.doi.org/10.1016/j.ijproman.2011.10.004

Hemanta Doloi a, Anil Sawhney b, K.C. Iyer b, Sameer Rentala (2012), Analyzing factors affecting delays in Indian construction projects, International journal of project management, http://dx.doi.org/10.1016/j.ijproman.2011.10.004

Iman Suleiman Al Maktoumi, (2020), assessing the factors causing project completion delays in the construction sector of Oman using sem-plS, Faculty of Business, Sohar University, Sultanate of Oman.

Kenley, R., & Seppänen, O. (2006). Location-based management for construction: Planning, scheduling, and control. Routledge.

Kamal, A., Abas, M., Khan, D., & Azfar, R. W. (2019). Risk factors influencing the building projects in Pakistan: from perspective of contractors, clients, and consultants. International Journal of Construction Management, 1-17.

Le-Hoai, L., Dai Lee, Y., & Lee, J. Y. (2008). Delay and cost overruns in Vietnam large construction projects: A comparison with other selected countries. KSCE journal of civil engineering, 12(6), 367-377.

Mamata Rajgor “Effective Techniques for Finding Delay in Construction Projects” (Volume 3, Issue 5, Jan 2016).

Maqsoom, A., Choudhry, R. M., Umer, M., & Mehmood, T. (2019). Influencing factors indicating time delay in construction projects: Impact of firm size and experience. International Journal of Construction Management, 1-12.

Martinsuo, M. & Lehtonen, P. (2008). Project autonomy in complex stakeholder environments: case study in non-profit service R&D. Paper presented at PMI®️ Research Conference: Defining the Future of Project Management, Warsaw, Poland. Newtown Square, PA: Project Management Institute.

Marzouk, M. M., & El-Rasas, T. I. (2014). Analyzing delay causes in Egyptian construction projects. Journal of advanced research, 5(1), 49-55.

Memon, A. H., Rahman, I. A., Abdullah, M. R., & Azis, A. A. A. (2014). Factors affecting construction cost performance in project management projects: Case of MARA large projects. International Journal of Civil Engineering and Built Environment, 1(1), 30-35.

Nistorescu, T., & Ploscaru, C. (2010). IMPACT OF ECONOMIC AND FINANCIAL CRISIS IN THE CONSTRUCTION INDUSTRY. Management & Marketing Journal, 8(1).

Owolabi, J. D., Amusan, L. M., Oloke, C. O., Olusanya, O., Tunji-Olayeni, P. F., Dele, O., ... & Omuh, I. O. (2014). Causes and effect of delay on project construction delivery time. International Journal of Education and Research, 2(4), 197-208.

Pınar Güngör (2011), The Relationship between Reward Management System and Employee Performance with the Mediating Role of Motivation: A Quantitative Study on Global Banks, 7th International Strategic Management Conference.

Pourrostam, T., & Ismail, A. (2011). Significant factors causing and effects of delay in Iranian construction projects. Australian Journal of Basic and Applied Sciences, 5(7), 450-456.

Rajgor, M., Paresh, C., Dhruv, P., Chirag, P., & Dhrmesh, B. (2016). RII & IMPI: effective techniques for finding delay in construction project. International Research Journal of Engineering and Technology, 3(1), 1173-1177.

Ramli, M. Z., Malek, M. A., Hamid, B., Roslin, N. T., Roslan, M. E. M., Norhisham, S., & Mohd, M. F. (2018). Influence of project type, location, and area towards construction delay: A review on significance level of delay factors. International Journal of Engineering and Technology (UAE), 7(4), 392-399.

Saiful Haq, Yahya Rashid, Ph.D., Muhammad Shakeel Aslam (2014), Effects of Delay in construction Projects of Punjab-Pakistan: An Empirical Study, Journal of Basic and Applied Scientific Research.

Sambasivan, M., & Soon, Y. W. (2007). Causes and effects of delays in Malaysian construction industry. International Journal of project management, 25(5), 517-526.

Saunders, M., Lewis, P., & Thornhill, A. (2009). Research Method for Business Students. Dehli: Pearson Education.

Shahsavand, P., Marefat, A., & Parchamijalal, M. (2018). Causes of delays in construction industry and comparative delay analysis techniques with SCL protocol. Engineering, Construction and Architectural Management.

Sheikh, A. H. A., Ikram, M., Ahmad, R. M., Qadeer, H., & Nawaz, M. (2019). Evaluation of key factors influencing process quality during construction projects in Pakistan. Grey Systems: Theory and Application.

Sohu, S., & Chandio, A. F. (2019). Identification of causes and minimization of delays in highway projects of Pakistan. Mehran University Research Journal of Engineering and Technology, 38(1), 103-112.

Taofeeq, D. M., Adeleke, A. Q., & Lee, C. K. (2020). The synergy between human factors and risk attitudes of Malaysian contractors’: Moderating effect of government p Towhid Pourrostam and Amiruddin Ismail “Causes and Effects of Delay in Iranian Construction Projects.” (Vol. 4, No. 5, October 2012) policy. Safety science, 121, 331-347.

Tumi, S. A. H., Omran, A., & Pakir, A. H. K. (2009, November). Causes of delay in construction industry in Libya. In the International Conference on Economics and Administration (pp. 265-272).

Ullah, F., Thaheem, M. J., Siddiqui, S. Q., & Khurshid, M. B. (2017). Influence of Six Sigma on project success in construction industry of Pakistan. The TQM Journal.

Zafar, I., Wuni, I. Y., Shen, G. Q., Ahmed, S., & Yousaf, T. (2019). A fuzzy synthetic evaluation analysis of time overrun risk factors in highway projects of terrorism-affected countries: the case of Pakistan. International Journal of Construction Management, 1-19.

Iman Suleiman Al Maktoumi, (2020), assessing the factors causing project completion delays in the construction sector of Oman using sem-plS, Faculty of Business, Sohar University, Sultanate of Oman.

# Appendix

## Appendix: A Questionnaire

| SECTION A: Respondent Background |  |  |  |
| --- | --- | --- | --- |
| State respondent organization/company type | - Client | State respondent position in the organization/company | - Project Manager |
|  | - Consultant |  | - Project Coordinator |
|  | - Contractor |  | - Site Manager |
|  | - Others |  | - Site Supervisor |
| State the number of year respondent has experienced in the construction industry | - < 5 Years | State the number of year respondent has experienced in the construction industry | - 1 - 3 Projects |
|  | - 5 - 10 Years |  | - 4 - 6 Projects |
|  | - 11 - 15 Years |  | - 7 - 9 Projects |
|  | - > 15 Years |  | - > 9 Projects |
| State the type of building which involved the most frequent for delays | - Residential Construction | State the number of project delays which is faced by respondent | - 1 - 3 Projects |
|  | - Commercial Construction |  | - 4 - 6 Projects |
|  | - Industrial Construction |  | - 7 - 9 Projects |
|  | - Others |  | - > 9 Projects |
| State the % ageage of a delay from estimated project duration | - 0 – 5 % |  |  |
|  | - 5% - 10% |  |  |
|  | - 10% - 15% |  |  |
|  | - 15% - 20% |  |  |
|  | - > 20% |  |  |

| SECTION B: Factors contributing to the delay of the project |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sr. # | Statement | Not Important | Slightly Important | Moderately Important | Very Important | Extremely Important |
| V-1: Contractor's Incompetency (Abdallah M. Odeh, 2002) |  |  |  |  |  |  |
| Rate according to the importance of the factor in cause delay in construction projects on a scale from 1-5 with 1 being not important and 5 being Extremely Important |  |  |  |  |  |  |
| 1 | Subcontractor mismanagement |  |  |  |  |  |
| 2 | Site Management issues |  |  |  |  |  |
| 3 | Improper Construction Method |  |  |  |  |  |
| 4 | Improper Planning |  |  |  |  |  |
| 5 | Mistakes during construction stage |  |  |  |  |  |
| 6 | Inadequate contractor experience |  |  |  |  |  |
| V-2: Client's Incompetency (Abdallah M. Odeh, 2002) |  |  |  |  |  |  |
| Rate according to the importance of the factor in cause delay in construction projects on a scale from 1-5 with 1 being not important and 5 being Extremely Important |  |  |  |  |  |  |
| 1 | Finances and payment of completed work |  |  |  |  |  |
| 2 | Owner interference |  |  |  |  |  |
| 3 | Unrealistic contract duration and requirement imposed by the client |  |  |  |  |  |
| 4 | Slow decision making |  |  |  |  |  |
| V-3: Consultant's Incompetency (Abdallah M. Odeh, 2002) |  |  |  |  |  |  |
| Rate according to the importance of the factor in cause delay in construction projects on a scale from 1-5 with 1 being not important and 5 being Extremely Important |  |  |  |  |  |  |
| 1 | Delay in approving or preparation of shop drawings by the consultant |  |  |  |  |  |
| 2 | Poor contract management |  |  |  |  |  |
| 3 | Lack of Quality assurance and control |  |  |  |  |  |
| 4 | Delay in approval of tests and inspection |  |  |  |  |  |
| V-4: EEFs (Abdallah M. Odeh, 2002) |  |  |  |  |  |  |
| Rate according to the importance of the factor in cause delay in construction projects on a scale from 1-5 with 1 being not important and 5 being Extremely Important |  |  |  |  |  |  |
| 1 | Weather conditions |  |  |  |  |  |
| 2 | Regulatory Changes |  |  |  |  |  |
| 3 | Problem With neighbors |  |  |  |  |  |
| 4 | Unforeseen ground conditions |  |  |  |  |  |
| Sr No. | Statement | Strongly Disagree | Disagree | Uncertain | Agree | Strongly Agree |
| V-5: OPAs (Güngör, 2011) |  |  |  |  |  |  |
| Rate according to the importance of the factor in increasing the performance of employees on a scale from 1-5 with 1 strongly disagree and 5 being strongly agree |  |  |  |  |  |  |
| 1 | Financial rewards (salary, bonus, and perquisite) (Güngör, 2011) |  |  |  |  |  |
| 2 | Price increases of salary raises performance of the employee. (Güngör, 2011) |  |  |  |  |  |
| 3 | Benefits such as rent, clothing or fuel (Güngör, 2011) |  |  |  |  |  |
| 4 | Bonuses given on special days (Güngör, 2011) |  |  |  |  |  |
| V-6: Level of Autonomy for Project Manager |  |  |  |  |  |  |
| Rate according to the importance of the factor in increasing the performance of employees on a scale from 1-5 with 1 strongly disagree and 5 being strongly agree |  |  |  |  |  |  |
| 1 | The project Manager could freely choose tolls and technologies |  |  |  |  |  |
| 2 | The project Manager had control over what he was supposed to accomplish |  |  |  |  |  |
| 3 | The project Manager was granted autonomy on how to handle all requirements and changes |  |  |  |  |  |
| 4 | The project Manager was free to assign personnel to the Project |  |  |  |  |  |
| Sr No. | Statement | Very Low | Low | Average | High | Very High |
| V-7: Project Location (Hemanta Doloi a, ⁎, Anil Sawhney b, K.C. Iyer b, Sameer Rentala) |  |  |  |  |  |  |
| Rate according to the importance of the factor in cause delay in construction projects on a scale from 1-5 with (1 very low, 2 low,3 average, 4 high, 5 very high) |  |  |  |  |  |  |
| 1 | Restricted access at site |  |  |  |  |  |
| 2 | Extreme weather conditions |  |  |  |  |  |
| 3 | Slow decisions from owner |  |  |  |  |  |
| 4 | Delay in material delivery by vendors |  |  |  |  |  |
| 5 | Site accidents due to negligence |  |  |  |  |  |
| 6 | Site accidents due to lack of safety measures |  |  |  |  |  |
| 7 | Unforeseen ground conditions |  |  |  |  |  |
| 8 | Hostile political conditions |  |  |  |  |  |
| 9 | Inaccurate specification of site condition |  |  |  |  |  |

| Sr. No. | Statement |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| V-8A: Effects of delays in projects (Number) (Wei, K.S., 2010) |  |  |  |  |  |  |
| Rate according to the importance of delay in construction projects on the on probability of occurrence of an event of the a scale from 1-5 Frequency of these outcomes will be measured on five point Likert-type scale i.e. 1 = 0 Project; 2 = 1 to 5 projects; 3 = 6 to 10projects; 4 = 10 to 15 projects and 5 = More than 15 projects. |  |  |  |  |  |  |
| 1 | Cost Over run | 0 | 1 to 5 | 6 to 10 | 11 to 15 | >15 |
| 2 | Time overrun |  |  |  |  |  |
| 3 | Litigation |  |  |  |  |  |
| 4 | Abandonment |  |  |  |  |  |
| V-8B: Effects of delays in projects (Amount) (Wei, K.S., 2010) |  |  |  |  |  |  |
| Rate according to the importance of delay in construction projects on the on probability of occurrence of an event of the a scale from 1-5 scale is about % ageage amount of cost overrun, time overrun, litigation and abandonment and measured on five point Likert-type scale i.e. 1= 0%; 2 = 0%1 to 10%; 3 = 11% to 20%; 4 = 21% to 30%; 5 = More than 30%. |  |  |  |  |  |  |
| 1 | Cost Over run | 0% | 1 to 10% | 11 to 20% | 21 to 30% | >30% |
| 2 | Time overrun |  |  |  |  |  |
| 3 | Litigation |  |  |  |  |  |
| 4 | Abandonment |  |  |  |  |  |